UPDATED AS PER OFFICIAL LOA:
• Scope revised from full Maharashtra coverage to Nagpur Region + C.S.N. Region only.
• Project timeline revised from May 4, 2026 – November 3, 2026 to May 4, 2026 – November 3, 2026.
• Timeline, deployment phases, and regional references updated accordingly.

MAHARASHTRA STATE ELECTRICITY DISTRIBUTION CO. LTD.

MSEDCL  |  Powering Maharashtra

PROJECT EXECUTION BLUEPRINT Electric Pole Geo-Mapping & AI-Powered Infrastructure Intelligence System Nagpur Region + C.S.N. Region T0: May 4, 2026 → T6: November 3, 2026

| Document Version | Project Status | T0 (Start) | T6 (End) | Classification |
| --- | --- | --- | --- | --- |
| V1.0 — 2026 | ACTIVE BLUEPRINT | May 4, 2026 | November 3, 2026 | CONFIDENTIAL |

# Table of Contents

Table of Contents	2

Chapter 1: Executive Summary	6

1.1 Project Overview	6

1.2 Project Vision	6

1.3 Core Problem Being Solved	6

1.4 6-Month Execution Summary	7

1.5 Key Deliverables — September 30, 2026	7

1.6 Project Scale	7

1.7 Three Systems Combined — The Strategic Advantage	8

Chapter 2: Introduction	9

2.1 About MSEDCL	9

2.2 Background and Context	9

2.3 The Digital Infrastructure Gap	9

2.4 Why a 6-Month Compressed Timeline?	10

2.5 Scope of This Blueprint	10

Chapter 3: Objectives	11

3.1 Primary Objectives	11

3.2 Secondary Objectives	11

3.3 SMART Objectives Framework	11

3.4 Key Performance Indicators (KPIs)	12

Chapter 4: Study Area — Ground Reality	13

4.1 Maharashtra State — Geographic Profile	13

4.2 MSEDCL Circle-wise Coverage Map	13

4.3 Terrain Classification — Survey Approach per Zone	14

4.4 Estimated Pole Distribution	14

4.5 Pilot District — Selection & Rationale	14

Chapter 5: System Architecture & Technology	16

5.1 System Architecture — Three-Layer Design	16

5.2 Mobile Survey Application	16

5.2.1 Core Features	17

5.2.2 Data Fields Captured per Pole	17

5.3 Backend & Cloud Architecture	17

5.4 AI Dashboard — MSEDCL's Primary Intelligence Interface	18

Dashboard Modules	18

5.5 Software Licenses & Tools	18

Chapter 6: Methodology	20

6.1 Methodology Philosophy — Scan-Tag-Verify-Classify-Integrate	20

6.2 Mobile Survey Workflow	20

Step 1: Pre-Survey Preparation (Every Morning)	20

Step 2: Active Survey (08:00 – 16:30)	20

Step 3: Sync & End-of-Day	20

6.3 Drone Survey Workflow	20

When Drone is Deployed	20

Drone Workflow	21

6.4 Quality Assurance (QA) Framework	21

6.5 Unique Pole ID (UID) System	21

6.6 Data Collection Standards	21

Chapter 7: Implementation Plan & Timeline	23

7.1 Phase Overview — 6-Month Master Plan	23

7.2 Phase 0 — Pre-Deployment Setup (May 1–7, 2026)	23

Technology Readiness (Days 1–7)	23

Pilot District Preparation (Days 1–7)	23

7.3 Phase 1 — Pilot Execution (May 1–21, 2026)	24

Pilot Success Criteria	24

7.4 Phase 2 — Mass Hiring & Training (May 1–21, parallel)	24

7.5 Phase 3 — Full Maharashtra Deployment (May 22 – August 15, 2026)	24

District Coordinator Weekly Reporting Rhythm	25

7.6 Phase 4 — Validation & Completion (August 16 – September 15, 2026)	25

7.7 Phase 5 — AI Dashboard, Handover & Closeout (September 1–30, 2026)	25

7.8 Critical Milestones Calendar	25

7.9 Parallel Workstreams — Week-by-Week Summary	26

Chapter 8: AI Integration — Models, Automation & AI Dashboard	27

8.1 AI Strategy for 6-Month Timeline	27

8.2 AI Model 1 — Pole Type Classifier	27

8.3 AI Model 2 — Pole Condition Assessor	27

8.4 AI Model 3 — Predictive Maintenance Engine	28

8.5 AI Model 4 — Automated Data Quality Checker	29

8.6 AI Development Timeline — Week by Week	29

8.7 Data Labeling Strategy	29

8.8 AI Infrastructure Requirements	30

Chapter 9: Manpower Planning	31

9.1 Organisation Structure	31

9.2 Complete Role Directory	31

9.2.1 Core Management & Leadership	31

9.2.2 Technology Team	32

9.2.3 Field Team	33

9.2.4 Support Functions	33

9.3 Hiring Timeline — Critical Path	34

9.4 Recruitment Strategy	35

Surveyor Recruitment (~120 — Volume Hiring in 7 Days)	35

Technical / Management Roles	35

9.5 Training Program — 5-Day Module	35

9.6 Safety & Personnel Policy	35

Chapter 10: Infrastructure & Logistics	37

10.1 Infrastructure Overview	37

10.2 Field Devices & Accessories — Complete List	37

10.3 Vehicles & Transportation	38

10.4 Office Infrastructure	39

10.4.1 Central Project HQ	39

10.4.2 District Field Offices (14)	39

10.5 Drone Operations — Agency Selection	40

Minimum Requirements for Drone Agency	40

10.6 Annual Maintenance Contracts (AMC)	40

10.7 Communication Infrastructure	41

Chapter 11: Budget Framework	42

11.1 Budget Notes & Assumptions	42

11.2 Capital Expenditure (CapEx) — One-Time Procurement	42

A. Field & Office Devices	42

B. Technology Development (CapEx)	43

11.3 Operational Expenditure (OpEx) — 6 Months	43

A. Cloud & Software Costs	43

B. Field Operations Costs	44

C. Human Resource Costs	44

11.4 Budget Summary	45

Chapter 12: Permissions, Licensing & Legal Framework	47

12.1 MSEDCL Internal Authorizations	47

12.2 Drone / UAV Regulatory Approvals — DGCA	47

12.3 State / District Level Permissions	48

12.4 Data Privacy & Security Compliance	48

12.5 Permission Timeline Tracker	49

Chapter 13: Risk Management	50

13.1 Risk Context — 6-Month Compressed Timeline	50

13.2 Risk Register	50

13.3 Critical Risk Response Plans	51

R01 — MSEDCL Non-Cooperation (CRITICAL)	51

R02 — Mass Hiring in 3 Weeks (CRITICAL)	51

R05 + R09 — Monsoon + Summer Attrition	52

R11 — Field Safety Incidents (CRITICAL SEVERITY)	52

Chapter 14: Standard Operating Procedures & Monitoring	53

14.1 Daily Operational Rhythms	53

Surveyor — Daily SOP	53

Supervisor — Daily SOP	53

District Coordinator — Daily SOP	54

14.2 Data Management SOP	54

14.3 AI System SOP	54

14.4 Monitoring Dashboard — Management View	55

KPIs Visible in Real-Time	55

14.5 Escalation Matrix	55

14.6 Points of Contact (POC)	56

Internal Project Team	56

External / MSEDCL Points of Contact	56

14.7 Reporting Structure	57

Chapter 15: Final Deliverables — September 30, 2026	59

D1 — Complete GIS Map of All Maharashtra Poles	59

D2 — Central Pole Asset Database	59

D3 — AI System — Operational & Deployed	60

D4 — AI Dashboard — MSEDCL Intelligence Interface	60

Dashboard Feature Modules	60

D5 — Final Project Report	61

15.1 Deliverables Master Tracker	62

Appendices	64

Appendix A: Glossary of Terms	64

Appendix B: 6-Month Master Timeline — Gantt Summary	65

Appendix C: Pole Condition Reference Guide (Field Card)	65

Appendix D: Complete Pole Data Field Reference (30+ Fields)	66

Appendix E: Technology Stack Reference	67

# Chapter 1: Executive Summary

## 1.1 Project Overview

Maharashtra State Electricity Distribution Co. Ltd. (MSEDCL) operates one of India's largest electricity distribution networks, serving over 2.9 crore consumers across Nagpur Region + C.S.N. Region of Maharashtra. The backbone of this network — millions of electric poles — currently exists without any centralized, GPS-tagged, digitally accessible asset record.

This blueprint presents the complete execution plan for the MSEDCL Electric Pole Geo-Mapping and AI-Powered Infrastructure Intelligence System — a technology-driven initiative to survey, map, classify, and manage every electric pole in Maharashtra within a single, aggressive 6-month window.

⚠ CRITICAL PROJECT PARAMETER T0 = May 4, 2026 (Project Start — Day Zero (Updated as per LOA)) T6 = November 3, 2026 (Full Completion & Handover) Total Duration = 6 Months (183 days) This is a high-intensity, compressed-timeline deployment. Every week counts.

## 1.2 Project Vision

★ To create a first-of-its-kind, AI-powered, GIS-enabled, real-time electric pole asset registry covering ALL Nagpur Region + C.S.N. Region of Maharashtra — fully surveyed, classified, and handed over to MSEDCL within 6 months from May 4, 2026.

## 1.3 Core Problem Being Solved

| Problem | Impact on MSEDCL | Our Solution |
| --- | --- | --- |
| No GPS coordinates for poles | They can locate assets but limited to manual efforts as of now. | Mobile + Drone geo-tagging |
| No centralized pole database | Data fragmented across 1,000+ sub-divisions | Cloud-based central repository |
| Manual inspection | Slow, error-prone, dangerous | AI visual classification from photos |
| No condition monitoring | Purely reactive maintenance | AI condition scoring (1–5 scale) |
| No asset lifecycle tracking | Unknown pole age & full history | Unique Pole ID + digital history |
| High operational cost | Inefficient unplanned manpower use | Predictive AI maintenance engine |

## 1.4 6-Month Execution Summary

| Month | Period | Phase Name | Key Focus |
| --- | --- | --- | --- |
| Month 1 | May 4 – Apr 30 | Mobilization & Pilot | Hiring, training, system setup, 2-week pilot in 1 district |
| Month 2 | May 1 – May 31 | Full Deployment — Wave 1 | Nagpur Region + C.S.N. Region activated; ~120 surveyors in field |
| Month 3 | Jun 1 – Jun 30 | Intensive Survey + AI Go-Live | Peak survey operations; AI system deployed |
| Month 4 | Jul 1 – Jul 31 | Continuous Survey + QA | Data quality drive; AI model refinement; 60% target |
| Month 5 | Aug 1 – Aug 31 | Survey Completion + Integration | Complete remaining poles; GIS dashboard live |
| Month 6 | Sep 1 – Nov 3 | Validation, AI Handover & Closeout | Final validation, AI dashboard, handover to MSEDCL |

## 1.5 Key Deliverables — November 3, 2026

- Complete GIS map of all electric poles across Nagpur Region + C.S.N. Region of Maharashtra

- Central cloud database — every pole with full attributes, photos, and Unique Pole ID

- AI-powered pole classification system (type + condition) — operational and live

- AI Dashboard — MSEDCL management interface with full pole map, analytics, and features

- Final comprehensive project report submitted to MSEDCL

## 1.6 Project Scale

| Parameter | Value |
| --- | --- |
| Project Duration | 6 Months (May 4 – November 3, 2026) |
| Districts Covered | Nagpur Region + C.S.N. Region of Maharashtra — simultaneously |
| Estimated Total Poles | 55–75 Lakh (refined after pilot) |
| Pilot Phase | 2–3 weeks in 1 district (May 4–21, 2026) |
| Full Deployment Start | May 25, 2026 (Nagpur Region + C.S.N. Region simultaneously) |
| Field Surveyors | ~120 (hired and trained within Month 1) |
| Field Supervisors | ~25 |
| Technology Stack | Mobile App + Cloud + AI/ML + GIS + Drone |
| AI System Live | By end of Month 3 (June 30, 2026) + 15 buffer days |
| Final Handover | November 3, 2026 |

## 1.7 Three Systems Combined — The Strategic Advantage

► FIELD SYSTEM → ~120 Surveyors + Mobile App + Drones = Real-Time Ground-Level Data ► DATA SYSTEM → Cloud + PostgreSQL/PostGIS + APIs = Centralized Scalable Infrastructure ► INTELLIGENCE SYSTEM → AI Models + Automation + AI Dashboard = Smart Decision Making This is NOT a survey project. It is a SMART INFRASTRUCTURE INTELLIGENCE SYSTEM that will serve MSEDCL for the next 20+ years.

# Chapter 2: Introduction

## 2.1 About MSEDCL

| Parameter | Details |
| --- | --- |
| Established | 2005 (following MSEB restructuring under Electricity Act, 2003) |
| Headquarters | Mumbai, Maharashtra |
| Service Area | Nagpur Region + C.S.N. Region of Maharashtra (excl. Mumbai city) |
| Consumer Base | Approx. 2.9 Crore consumers |
| Employee Strength | ~80,000+ |
| Circles / Divisions | 15 Circles, 50+ Divisions, 1,000+ Sub-Divisions |
| Annual Revenue | Approx. ₹70,000 Crore+ |
| Network | Lakhs of KM of LT/HT/EHT lines across Nagpur Region + C.S.N. Region |

## 2.2 Background and Context

Electric distribution poles form the critical last-mile infrastructure that connects power generation to every consumer — every lit home, every running factory, every hospital. Despite their absolute operational criticality, MSEDCL currently has no comprehensive, geo-tagged, digitally accessible inventory of its pole network across Maharashtra.

As of May 2026, pole records are maintained in paper registers at sub-division level, no GPS coordinates are linked to individual poles, condition assessment happens only during reactive maintenance, and there is no centralized visibility for planning, compliance, or infrastructure investment decisions.

As Maharashtra's energy demand rises year on year, infrastructure failures caused by aged, damaged, or untracked poles result in consumer outages, expensive emergency repairs, and avoidable accidents. The need for technology-first asset management has reached a point of urgency that this project is directly designed to address.

## 2.3 The Digital Infrastructure Gap

★ KEY INSIGHT: In May 2026, MSEDCL can accurately tell you how many units of electricity were consumed in a village last month — but cannot tell you how many poles stand in that village, what condition they are in, when they were last inspected, or where exactly they are on a map. THIS is the gap that this 6-month project will permanently close.

## 2.4 Why a 6-Month Compressed Timeline?

- MSEDCL's strategic modernization roadmap demands immediate action — not a multi-year program

- Mobile + AI + GIS technology in 2026 enables high-speed, high-quality field data collection at scale

- Parallel deployment across Nagpur Region + C.S.N. Region simultaneously — enabled by the 300-surveyor field force — makes 6 months achievable

- Regulatory and compliance pressures from CEA and CERC for digital asset records are time-sensitive

- Smart Grid and Smart Metering initiatives require a foundational pole asset layer — urgently

## 2.5 Scope of This Blueprint

This document is the definitive Project Execution Blueprint for the MSEDCL Pole Mapping & AI System. It covers every aspect of project delivery — field operations, technology architecture, AI development, manpower planning, budget, permissions, risk management, SOPs, and final deliverables. All timelines are anchored to T0 = May 4, 2026.

# Chapter 3: Objectives

## 3.1 Primary Objectives

- Conduct a complete geo-referenced survey of every electric pole across Nagpur Region + C.S.N. Region of Maharashtra by November 3, 2026.

- Assign a permanent Unique Pole ID (UID) to every pole surveyed — creating a digital identity for each asset for its entire operational lifecycle.

- Capture 30+ attributes per pole including GPS coordinates, pole type, material, height, circuit type, condition score, equipment attached, and ownership zone.

- Build a centralized, cloud-hosted pole asset database accessible in real-time to all authorized MSEDCL circles and divisions.

- Deploy an AI-powered classification system for automated pole type recognition and condition assessment — live by end of Month 3 (June 30, 2026).

- Deliver a fully functional AI Dashboard — MSEDCL's primary interface for viewing the pole map, analytics, alerts, and maintenance intelligence.

- Integrate drone-based aerial mapping for forest, tribal, and difficult-terrain areas where ground survey is constrained.

- Complete formal handover of all systems, data, documentation, and trained MSEDCL staff by November 3, 2026.

## 3.2 Secondary Objectives

- Enable predictive maintenance by identifying high-risk poles before failure occurs

- Reduce future field inspection costs through AI-assisted remote condition monitoring

- Provide district-wise and division-wise asset inventory reports for MSEDCL annual planning

- Build a digital maintenance history log per pole for regulatory compliance and audit trails

- Serve as the foundational asset layer for MSEDCL's long-term Smart Grid initiative

## 3.3 SMART Objectives Framework

| Objective | Specific | Measurable | Achievable | Relevant | Time-bound |
| --- | --- | --- | --- | --- | --- |
| Pole Survey | Nagpur Region + C.S.N. Region | Total pole count | ~120 surveyors deployed | Core asset data | By Nov 3, 2026 |
| Unique ID | Every pole | 100% UID assigned | Mobile app auto-gen | Lifecycle tracking | During survey |
| AI Classification | Type + Condition | ≥90% accuracy | Transfer learning ML | Ops & safety | By Jun 30, 2026 |
| AI Dashboard | Live MSEDCL interface | All features live | Cloud + GIS platform | Management ops | By Aug 31, 2026 |
| Central Database | All pole attributes | 100% data stored | Cloud redundancy | Planning & audit | By Nov 3, 2026 |

## 3.4 Key Performance Indicators (KPIs)

| KPI | Target | Measurement Method | Review Frequency |
| --- | --- | --- | --- |
| Survey Completion Rate | ≥ 98% of all poles | DB count vs. estimate | Weekly |
| Daily Survey Productivity | ≥ 50 poles / surveyor / day | App-based daily tracking | Daily |
| GPS Accuracy | ± 3 meters or better | Drone cross-validation | Weekly sampling |
| Data Completeness | ≥ 95% fields filled / record | Automated QC check | Daily |
| AI Model Accuracy — Type | ≥ 90% on validation set | Hold-out test dataset | Monthly |
| AI Model Accuracy — Condition | ≥ 85% on validation set | Ground-truth comparison | Monthly |
| Dashboard Uptime | ≥ 99.5% availability | Cloud monitoring alerts | Continuous |
| Pilot Completion | 100% pilot district in 3 weeks | Milestone tracker | End of Week 3 |
| AI System Live | Deployed by Jun 30, 2026 | Production deployment log | End of Month 3 |
| Final Handover | 100% by Nov 3, 2026 | Handover checklist sign-off | End of Month 6 |

# Chapter 4: Study Area — Ground Reality

## 4.1 Maharashtra State — Geographic Profile

| Parameter | Data |
| --- | --- |
| Total Area | 3,07,713 sq. km (3rd largest state in India) |
| Total Districts | 14 (Nagpur Region + C.S.N. Region) |
| MSEDCL Circles | 15 Circles |
| MSEDCL Divisions | ~50 Divisions |
| MSEDCL Sub-Divisions | ~1,000+ Sub-Divisions |
| Agro-climatic Zones | 5 — Vidarbha, Marathwada, Konkan, Western Maharashtra, North Maharashtra |
| Total Villages | ~44,000 |
| Urban Local Bodies | ~534 |
| Topography | Coastal plains, Western Ghats, Deccan plateau, river valleys, semi-arid zones |

## 4.2 MSEDCL Circle-wise Coverage Map

| Circle | Key Districts | Terrain Challenge | Survey Priority |
| --- | --- | --- | --- |
| Pune | Pune, Satara (part) | Dense urban + peri-urban | High — urban complexity |
| Nashik | Nashik, Dhule, Nandurbar | Semi-arid + hilly + tribal | High — pilot candidate |
| Aurangabad | Aurangabad, Jalna, Beed | Marathwada dry, remote villages | High |
| Nagpur | Nagpur, Wardha | Urban + agricultural mix | High |
| Amravati | Amravati, Akola, Washim | Vidarbha heat, some forest | Medium-High |
| Latur | Latur, Osmanabad, Nanded | Arid, sparsely connected | Medium |
| Konkan | Ratnagiri, Sindhudurg | Coastal, dense forest, access issues | Medium — drone needed |
| Kolhapur | Kolhapur, Sangli, Solapur | Flat agricultural, accessible | Medium |
| Thane | Thane, Palghar, Raigad | Urban sprawl + tribal forest | High — drone needed |
| Chandrapur | Chandrapur, Gadchiroli | Dense forest, tribal, LWE sensitivity | High — drone + permissions |
| Other Circles (5) | Remaining districts | Mixed terrain | Standard |

## 4.3 Terrain Classification — Survey Approach per Zone

| Terrain Type | % of State | Representative Districts | Primary Survey Method |
| --- | --- | --- | --- |
| Urban / Peri-urban | ~15% | Pune, Nagpur, Nashik, Thane, Aurangabad | Mobile app — dense data, vehicle not always needed |
| Agricultural Flat Plains | ~45% | Vidarbha, Marathwada, W. Maharashtra | Mobile app + motorcycle — high productivity zone |
| Semi-arid / Rocky Terrain | ~15% | Marathwada, N. Maharashtra | Mobile app + 4WD SUV for team transport |
| Hilly / Western Ghats | ~10% | Konkan, Kolhapur, E. Nashik | Mobile + drone for ridge-line areas |
| Dense Forest / Tribal | ~10% | Gadchiroli, Chandrapur, Palghar, Nandurbar | Drone primary + limited ground team |
| Coastal / Wetland | ~5% | Ratnagiri, Sindhudurg, Raigad | Mobile + drone + boat (select areas) |

## 4.4 Estimated Pole Distribution

| Pole Category | Estimated Count | Basis |
| --- | --- | --- |
| LT Distribution Poles (last-mile) | 35–45 Lakh | ~1 pole per 5–8 LT consumers |
| HT Line Poles / Structures | 8–12 Lakh | HT network route length estimates |
| 11 kV Feeder Poles | 5–8 Lakh | Feeder route lengths from MSEDCL |
| Service Connection Support Poles | 2–4 Lakh | Dense urban area estimates |
| Pole-Mounted Transformers | 1.5–2.5 Lakh | MSEDCL transformer count data |
| MSEDCL-Owned Street Light Poles | 1–2 Lakh | Municipal distribution data |
| TOTAL ESTIMATED POLES | 55–75 Lakh | Subject to pilot validation — May 2026 |

## 4.5 Pilot District — Selection & Rationale

The 2–3 week pilot (May 4–21, 2026) will be conducted in one district before the full 36-district simultaneous rollout begins on May 25, 2026.

| Selection Criterion | Requirement |
| --- | --- |
| Terrain mix | Must include urban, semi-urban, and rural poles for comprehensive testing |
| MSEDCL cooperation | Active divisional office willing to participate in pilot coordination |
| District size | Medium-size — large enough to be representative, manageable in 3 weeks |
| Existing records | Some partial MSEDCL records available for cross-validation |
| Security / access | No restricted security zones that would delay early-stage fieldwork |
| Connectivity | Good 5G network coverage for real-time data sync during pilot testing |

Recommended Pilot District: Nashik District — meets all criteria; accessible from Pune/Mumbai; diverse terrain mix; strong MSEDCL divisional presence. Final selection to be confirmed with MSEDCL management at project kick-off.

# Chapter 5: System Architecture & Technology

## 5.1 System Architecture — Three-Layer Design

## 5.2 Mobile Survey Application

### 5.2.1 Core Features

- GPS auto-capture with real-time accuracy indicator — submission blocked if accuracy > 5 metres

- Auto-generation of Unique Pole ID (UID) on record creation — no manual entry needed

- Offline-first architecture — data stored in SQLite locally; syncs to cloud when 2G+ available

- Guided structured form with dropdowns and validation — minimizes free-text errors

- Mandatory 3-photo capture (full pole view, base/foundation, top/equipment)

- Real-time duplicate alert — warns surveyor if within 10m radius of existing submitted pole

- Supervisor QC mode — review, approve, reject, or return records for correction

- Battery and data usage optimization for 8+ hour uninterrupted field use

- Daily productivity counter — shows surveyor their running total against daily target

### 5.2.2 Data Fields Captured per Pole

| Category | Fields Captured |
| --- | --- |
| Identity | Unique Pole ID (auto), MSEDCL existing tag (if found), Survey date-time, Surveyor ID |
| Location | GPS Latitude, GPS Longitude, GPS Altitude, GPS Accuracy (m), Village/Ward, Sub-division, Division, Circle, District |
| Physical Attributes | Pole material (CC/Steel/Wooden/Tubular), Height range, Condition score (1–5), Tilt observed (Y/N), Visible cracks/damage (Y/N) |
| Electrical Attributes | Line type (LT/HT/11kV/33kV), Phase (Single/Three), Number of circuits, Transformer mounted (Y/N), Street light attached (Y/N) |
| Equipment on Pole | DO Fuse, LA (Lightning Arrester), Isolator, LT Distribution Box, Service cable count, Other equipment |
| Photos | Photo 1 (Full view), Photo 2 (Base/Foundation), Photo 3 (Top/Equipment), Photo 4 (Damage/Special — optional) |
| Observations | Safety concern flag (Y/N — triggers immediate priority review), Remarks (max 200 characters) |

## 5.3 Backend & Cloud Architecture

| Component | Technology | Purpose |
| --- | --- | --- |
| Cloud Provider | AWS / Azure / NIC Cloud (TBD by Month 1) | Hosting, compute, storage, CDN |
| Application Server | Python FastAPI | REST API services, business logic, authentication |
| Primary Database | PostgreSQL 15 + PostGIS 3 | Pole records with full spatial query capability |
| Photo / File Storage | AWS S3 / Azure Blob Storage | All pole photos (3–4 per pole, estimated 200–300 TB total) |
| GIS Map Server | GeoServer | Tile rendering, spatial queries, WMS/WFS services |
| Message Queue | RabbitMQ / AWS SQS | Async sync from 300+ mobile devices simultaneously |
| Cache Layer | Redis | Dashboard performance — fast map tile serving |
| Authentication | OAuth 2.0 + JWT tokens | Role-based access control (MSEDCL hierarchy) |
| API Gateway | AWS API Gateway / NGINX | Rate limiting, security, routing |
| Monitoring | Grafana + Prometheus | System health, uptime alerts, data pipeline monitoring |
| Backup | Daily automated to secondary region | Disaster recovery — 30-day point-in-time restore |
| Mobile Sync CDN | CloudFront / Azure CDN | Fast offline map tile downloads for field devices |

## 5.4 AI Dashboard — MSEDCL's Primary Intelligence Interface

The AI Dashboard is the flagship deliverable of the Intelligence Layer — a fully web-based, role-accessible interface where MSEDCL management can view, analyse, and act on the complete pole network.

### Dashboard Modules

- Live Pole Map — Interactive GIS map of all surveyed poles across Maharashtra; filter by district, circle, division, pole type, condition, risk level

- District / Circle Progress Panel — Real-time survey completion percentage per district with RAG (Red/Amber/Green) status

- Condition Heat Map — Geographic visualization of pole condition distribution — identify high-risk zones instantly

- Priority Alert Board — Top poles flagged as Critical (Score 5) or Poor (Score 4) requiring immediate maintenance attention

- AI Classification Dashboard — Breakdown of pole types and condition scores auto-classified by AI models

- Predictive Maintenance Calendar — AI-generated maintenance schedule showing poles due for inspection by month

- Analytics & Trends — Charts showing survey progress over time, condition distribution, district comparisons

- Custom Report Generator — Export pole reports by district/circle/division/condition/type in CSV, Excel, PDF

- Drone Survey Status — Overlay of drone-covered zones vs. ground-surveyed zones

- User Management — MSEDCL role-based access: Corporate view, Circle SE view, Division EE view

## 5.5 Software Licenses & Tools

| Software / Tool | Category | License Type | Cost |
| --- | --- | --- | --- |
| ArcGIS | GIS Desktop Analysis | paid | 2L/year |
| PostgreSQL + PostGIS | Spatial Database | Open Source | Free |
| GeoServer | GIS Map Server | Open Source | Free |
| AWS / Azure Cloud | Cloud Hosting & Storage | Pay-as-you-use | To Be Finalized |
| React Native / Flutter | Mobile App Framework | Open Source | Free (dev cost only) |
| React.js / Vue.js | Dashboard Frontend | Open Source | Free (dev cost only) |
| TensorFlow 2.x / PyTorch | AI/ML Framework | Open Source | Free |
| Label Studio | AI Data Labeling Tool | Open Source | Free |
| MLflow | AI Experiment Tracking | Open Source | Free |
| Grafana + Prometheus | Monitoring & Alerting | Open Source | Free |
| DJI Ground Station Pro | Drone Mission Planning | Commercial per device | ~₹15,000/device |
| Pix4D / DroneDeploy | Drone Data Processing | Commercial Subscription | To Be Finalized |
| Google Workspace / MS 365 | Office & Collaboration | Commercial | To Be Finalized |

# Chapter 6: Methodology

## 6.1 Methodology Philosophy — Scan-Tag-Verify-Classify-Integrate

## 6.2 Mobile Survey Workflow

### Step 1: Pre-Survey Preparation (Every Morning)

- Team leader downloads offline zone map for assigned area (village/ward boundary)

- App displays today's target zone on map — surveyor must stay within assigned boundary

- Check sync status — all yesterday's records must show green (synced) before departing

- Confirm device battery >90%, power bank fully charged, SIM data active

### Step 2: Active Survey (08:00 – 16:30)

- Surveyor physically rides / walks along distribution lines in assigned zone

- On spotting a pole, open 'New Survey' in app — GPS auto-captures (waits for ≤5m accuracy)

- Fill all mandatory fields using guided dropdown form — takes 2–4 minutes per pole

- Capture 3 mandatory photos (full view, base, top) + 1 optional damage photo

- UID auto-generated and displayed — physically write UID on pole with permanent marker where no tag is placed

- App checks for nearby duplicates — alerts if another pole already recorded within 10m

### Step 3: Sync & End-of-Day

- App syncs every 15 minutes when 2G+ available; force-sync at end of day

- End-of-day report submitted in app: poles surveyed, issues encountered, tomorrow's zone request

- Charge phone to 100% overnight — ready for next day

## 6.3 Drone Survey Workflow

### When Drone is Deployed

- Dense forest / tribal areas: Gadchiroli, Chandrapur, Palghar, Nandurbar — drone is primary tool

- Western Ghats steep terrain: Konkan, E. Nashik — drone supplements limited ground access

- Monthly validation sweeps: Random 10% of completed survey zones cross-checked from air

### Drone Workflow

- Mission planning: Define automated flight path in DJI Ground Station / Pix4D Capture — 70% side overlap, 80% front overlap at 60–80m altitude

- DGCA NPNT compliance: Flight plan submitted via DigitalSky portal before every flight

- Automated flight execution: Drone captures orthophotos of entire assigned zone

- Data download and processing: Pix4D / DroneDeploy generates high-resolution orthomosaic map

- AI pole detection: Computer vision model detects pole locations from orthomosaic image

- Cross-reference: AI-detected poles compared against mobile survey database for the same zone

- Gap identification: Poles found by drone but absent in mobile data flagged for ground team revisit

## 6.4 Quality Assurance (QA) Framework

| QA Level | By Whom | Method | When |
| --- | --- | --- | --- |
| L1 — Surveyor Self-Check | Surveyor | App validation: mandatory fields, GPS accuracy, photo count — blocks submission if incomplete | Every single record |
| L2 — Supervisor Field QC | Field Supervisor | Reviews all team's records; physically spot-verifies 10% of submitted poles in the field | Daily |
| L3 — AI Auto-QC | AI QC Model (Model 4) | Automated photo quality check, GPS outlier detection, duplicate detection — runs on each sync | Real-time on sync |
| L4 — Central Data QC | Data Management Team | Statistical sampling; cross-district consistency checks; weekly data quality report | Weekly |
| L5 — Drone Validation | Drone Team + AI | Aerial cross-check of completed zones; identify missed poles | Monthly per district |

## 6.5 Unique Pole ID (UID) System

## 6.6 Data Collection Standards

| Standard | Protocol |
| --- | --- |
| GPS Coordinate System | WGS 84 (EPSG:4326) — universal standard; compatible with all GIS platforms |
| GPS Accuracy Threshold | ≤ 5 metres acceptable; ≤ 3 metres preferred; >5m blocked from submission |
| Photo Resolution Minimum | 8 Megapixel minimum; Full HD (1920×1080) — standard on all project devices |
| Photo Format & Size | JPEG; maximum 5MB per photo (compressed by app before sync to save data) |
| Date / Time Format | ISO 8601 (YYYY-MM-DD HH:MM:SS) with IST timezone — auto-captured by app |
| Condition Rating Scale | 1 = New/Excellent, 2 = Good, 3 = Fair/Watch, 4 = Poor/Priority, 5 = Critical/Urgent |
| Language | English for all system fields; Marathi or English for free-text remarks |
| Offline Storage Limit | Max 1,000 unsynced records before mandatory sync — prevents data accumulation risk |

# Chapter 7: Implementation Plan & Timeline

⚠ ALL DATES ANCHORED TO: T0 = May 4, 2026 ¦ T6 = November 3, 2026 Total project window = 6 months (183 days). Zero timeline slack.

## 7.1 Phase Overview — 6-Month Master Plan

| Phase | Period | Duration | Name | Core Objective |
| --- | --- | --- | --- | --- |
| Phase 0 | May 4 – Apr 7 | Week 1 (7 days) | Pre-Deployment Setup | System go-live check, core team mobilization, pilot district preparation |
| Phase 1 | May 4 – Apr 21 | 3 Weeks | Pilot Execution | Full survey of 1 district (Nashik); validate workflow; refine SOPs |
| Phase 2 | Apr 8 – Apr 21 | Parallel with Pilot | Mass Hiring & Training | Hire + train all ~120 surveyors and ~25 supervisors in parallel with pilot |
| Phase 3 | May 25 – Aug 15 | ~4 Months | Full Maharashtra Deployment | Nagpur Region + C.S.N. Region simultaneously; ~120 surveyors active; AI goes live Month 3 |
| Phase 4 | Aug 16 – Sep 15 | 1 Month | Validation & Completion | Gap-fill, drone sweeps, data quality drive, 100% coverage verification |
| Phase 5 | Sep 1 – Nov 3 | Final Month | AI Dashboard + Handover | AI dashboard final, MSEDCL training, documentation, formal handover |

## 7.2 Phase 0 — Pre-Deployment Setup (May 4–7, 2026)

### Technology Readiness (Days 1–7)

- Mobile survey app final build deployed to all pilot team devices (30 phones)

- Cloud infrastructure confirmed live — database, APIs, storage, GIS server all running

- Admin dashboard and supervisor review panel live and accessible

- Full end-to-end data pipeline tested: field → sync → database → dashboard

- DGCA drone permit applications submitted (Week 1 critical — 4–8 week processing time)

### Pilot District Preparation (Days 1–7)

- MSEDCL divisional office in Nashik briefed; cooperation letter issued

- 30 pilot surveyors and 6 supervisors selected (from pre-screened pool)

- Pilot team devices set up with app, SIM, power banks — field kits ready

- Pilot zone boundaries defined in app system by GIS team

- District Coordinator for Nashik assigned and briefed

## 7.3 Phase 1 — Pilot Execution (May 4–21, 2026)

| Week | Dates | Survey Focus | Parallel Activity |
| --- | --- | --- | --- |
| Week 1 | May 4–7 | Urban / town areas of Nashik — dense data, tests app under high-volume conditions | Mass hiring interviews running simultaneously |
| Week 2 | May 11–17 | Semi-rural and agricultural zones — tests rural workflow and GPS in flat terrain | Batch 1 of 150 surveyors training begins (5 days) |
| Week 3 | May 45–21 | Remote / hilly zones — tests offline mode, difficult terrain GPS | Batch 2 of 150 surveyors training; SOP updates from pilot feedback |

### Pilot Success Criteria

- 100% of Nashik district poles surveyed within 3 weeks

- Data completeness rate ≥ 95% on pilot records

- Average productivity of ≥ 50 poles/surveyor/day achieved

- No critical app failures or data loss incidents

- AI labeling team has ≥ 3,000 labeled images by end of pilot for model training

- Pilot report (SOP updates + per-pole cost actuals) completed by May 25

## 7.4 Phase 2 — Mass Hiring & Training (May 4–24, parallel)

| Activity | Dates | Output |
| --- | --- | --- |
| Hiring campaign launch | May 4 | Job postings on Naukri, college boards, employment exchanges, WhatsApp networks |
| Interview & shortlisting | May 4–7 | ~160 candidates shortlisted (~120 surveyors + ~25 supervisors + 10% buffer) |
| Training Batch 1 (180 pax) | May 8–12 | 5-day training; surveyors + supervisors; app, GPS, pole ID, safety, SOP |
| Training Batch 2 (180 pax) | May 12–19 | 5-day training; second batch; refreshed SOP from pilot week learnings |
| Device distribution + setup | May 19–24 | All 360 field devices set up, apps installed, SIMs active, field kits ready |
| District assignment | May 24 | All surveyors assigned to their specific district; District Coordinators briefed |

## 7.5 Phase 3 — Full Maharashtra Deployment (May 25 – August 15, 2026)

⚠ May 25, 2026: ALL 14 DISTRICTS GO LIVE SIMULTANEOUSLY ~120 surveyors deployed. ~25 supervisors active. 14 District Coordinators in place. This is the single largest coordinated field deployment day of the project.

| Month | Period | Survey Target | AI Milestone | Key Focus |
| --- | --- | --- | --- | --- |
| Month 2 | May 25 – May 31 | 15–20% of total poles (Nagpur Region + C.S.N. Region started) | AI training data accumulating | Stable deployment; productivity ramp-up; SOP adherence |
| Month 3 | Jun 1 – Jun 30 | 30–40% cumulative | AI MODELS GO LIVE — Jun 30 | Peak productivity; AI classification active; data quality drive |
| Month 4 | Jul 1 – Jul 31 | 55–65% cumulative | AI model refinement | Heavy districts (forest/tribal) drone ops; QA Level 4 audit |
| Month 5 | Aug 1 – Aug 15 | 75–80% cumulative | AI dashboard integration | Final push; hard-to-reach areas; gap filling begins |

### District Coordinator Weekly Reporting Rhythm

- Every Monday 09:00: Weekly target agreed with Field Ops Manager

- Every Friday 17:00: Weekly actuals submitted — poles completed, issues, attendance

- Every Sunday: Central data team runs district-wise completeness report

## 7.6 Phase 4 — Validation & Completion (September 16 – October 15, 2026)

- Identify all districts below 98% completion threshold — deploy additional surveyors

- Drone validation sweeps: All forest/tribal zones cross-checked from air

- Data Quality Audit: Every district record set reviewed for completeness and accuracy

- Gap-filling ground teams dispatched to areas flagged by drone or QC team

- All supervisor QC reviews completed; all pending approvals cleared

- Database locked for new standard submissions by October 15 (corrections-only mode)

## 7.7 Phase 5 — AI Dashboard, Handover & Closeout (October 1–November 3, 2026)

- September 1–15: AI Dashboard final testing and MSEDCL UAT (User Acceptance Testing)

- September 1–15: MSEDCL IT team training — 5 days hands-on system administration

- September 10–20: All documentation finalised — technical docs, user manuals, SOPs

- October 20–25: Formal MSEDCL data acceptance — sign-off on database completeness

- October 25–29: System access transfer — all credentials, source code, vendor contacts handed to MSEDCL

- November 3: Final Project Report submitted + Handover ceremony / sign-off meeting

## 7.8 Critical Milestones Calendar

| Milestone | Date | Owner | Success Criteria |
| --- | --- | --- | --- |
| M0 — Project Kick-Off | May 4, 2026 | Project Director | All core team assembled; app live; cloud live; pilot district ready |
| M1 — Pilot Complete | May 21, 2026 | Field Ops Manager | Nashik 100% surveyed; SOP finalized; pilot report ready |
| M2 — Full Deployment Day | May 25, 2026 | Project Manager | Nagpur Region + C.S.N. Region activated; ~120 surveyors in field simultaneously |
| M3 — AI System Live | June 30, 2026 | AI / Tech Lead | AI Models 1 & 2 deployed; auto-classifying all incoming records |
| M4 — 50% State Coverage | July 15, 2026 | Field + Data Teams | 18+ districts at ≥90% completion; central DB stable |
| M5 — Survey Complete | August 15, 2026 | Field Ops Manager | Nagpur Region + C.S.N. Region at ≥95% coverage; gap-filling underway |
| M6 — 100% Coverage Verified | October 15, 2026 | Data Manager + QC | All districts at ≥98%; drone validation done; database locked |
| M7 — AI Dashboard Live | October 20, 2026 | Tech Lead | All dashboard modules functional; MSEDCL UAT passed |
| M8 — Final Handover | November 3, 2026 | Project Director | Handover docs signed; MSEDCL access live; report submitted |

## 7.9 Parallel Workstreams — Week-by-Week Summary

| Workstream | May 4–21 | May 25–Jun 30 | Jul 1–Aug 15 | Aug 16–Nov 3 |
| --- | --- | --- | --- | --- |
| Field Survey | Pilot (1 district) | Full Nagpur Region + C.S.N. Region active | Intensive + difficult terrain | Gap-fill + validation |
| Hiring & Training | Mass hiring + 2 batches | Onboarding replacements | Minimal — only gap fills | Core team only |
| Tech / App Dev | Pilot fixes + enhancements | Ongoing improvements | Dashboard build | Final UAT + handover |
| AI Development | Data labeling starts | Training + deployment | Model refinement | Dashboard integration |
| Drone Operations | Pilot cross-check | Forest / tribal zones | Validation sweeps | Final aerial QC |
| QA / Data Quality | Pilot QA | Daily L1–L3 automated | Weekly L4 audit | Full L5 district QA |
| Reporting | Pilot report | Weekly status reports | Monthly dashboards | Final report + handover |

# Chapter 8: AI Integration — Models, Automation & AI Dashboard

## 8.1 AI Strategy for 6-Month Timeline

Given the compressed 6-month project window, the AI development strategy is optimized for parallel execution — AI model development runs concurrently with field survey operations from Day 1, with a hard go-live target of June 30, 2026 (end of Month 3). Data labeling begins immediately from the pilot phase, building training data volume rapidly so models are production-ready when field data volumes reach their peak.

## 8.2 AI Model 1 — Pole Type Classifier

| Parameter | Specification |
| --- | --- |
| Objective | Automatically identify pole material type from submitted field photos |
| Model Architecture | Transfer Learning on EfficientNet-B3 / ResNet-50 (pre-trained on ImageNet) |
| Input | 1–4 photos per pole submission (field-captured via survey app) |
| Output Classes | CC Concrete Pole / RCC Pole / Steel Lattice / Tubular Steel / Wooden Pole / Unknown |
| Training Dataset Target | Minimum 10,000 labeled images by May 31; 30,000+ by June 30 for production |
| Target Accuracy (Production) | ≥ 90% on held-out test dataset of 2,000 images |
| Inference Latency | < 3 seconds per pole record processed |
| Deployment Mode | Cloud API (FastAPI endpoint) — called automatically on every sync |
| Confidence Threshold | ≥ 70% confidence for auto-label; below 70% → flagged for human review |
| Go-Live Date | June 30, 2026 |

## 8.3 AI Model 2 — Pole Condition Assessor

| Score | Condition Label | Visual Indicators Detected by AI |  | Auto-Action Triggered |
| --- | --- | --- | --- | --- |
| 1 | New / Excellent | No damage indicators; clean surface; vertical alignment |  | Routine inspection schedule (5 years) |
| 2 | Good | Minor surface weathering; no structural issues; no lean |  | Routine schedule (3 years) |
| 3 | Fair / Watch | Surface rust patches; minor cracks; slight lean < 3° |  | Added to watchlist; 1-year inspection |
| 4 | Poor / Priority | Significant rust; visible cracks; lean 3–7°; base erosion |  | Maintenance work order within 3 months |
| 5 | Critical / Urgent | Structural failure risk; severe lean > 7°; broken/fractured base |  | IMMEDIATE alert + replacement work order |
| Parameter |  |  | Specification |  |  |
| Model Architecture |  |  | Multi-label CNN + Object Detection (YOLOv8 for defect localization) |  |  |
| Training Dataset Target |  |  | 15,000+ labeled and condition-graded images by June 30 |  |  |
| Target Accuracy |  |  | ≥ 85% on condition scoring validation set |  |  |
| Special Feature |  |  | Defect bounding box — highlights crack/rust location on photo in the dashboard |  |  |
| Go-Live Date |  |  | June 30, 2026 (simultaneous with Model 1) |  |  |

## 8.4 AI Model 3 — Predictive Maintenance Engine

With 3–4 months of incoming survey data before handover, a basic predictive maintenance engine can be built from Month 4 onwards and refined for handover.

| Input Feature | Data Source | Available From |
| --- | --- | --- |
| Pole condition score | AI Model 2 output | July 2026 |
| Pole type and material | AI Model 1 output | July 2026 |
| Geographic zone / climate | GIS layer — district and terrain type | May 2026 |
| Proximity to coast / forest | Spatial join with environmental GIS layers | May 2026 |
| Pole age (where known) | MSEDCL records (where available) | Variable |
| Fault history near pole | MSEDCL complaint data (integration required) | Integration Phase |

- Model Output: Risk score (0–100) per pole; poles above threshold added to maintenance priority list

- Target: First predictive report generated by August 31, 2026; handed over with model to MSEDCL

## 8.5 AI Model 4 — Automated Data Quality Checker

This model runs in real-time on every sync event — ensuring the database receives only clean, validated data. It is the fastest to build (rule-based + lightweight ML) and will be live from the first day of Phase 3 (May 25).

- GPS outlier detection — flags pole coordinates outside assigned district boundary

- Duplicate proximity detection — flags submissions within 5m of an existing record

- Photo blur detection — rejects photos below minimum sharpness threshold

- Photo relevance check — rejects photos that don't appear to show a pole

- Field completeness enforcement — blocks database entry for records missing mandatory fields

- Surveyor anomaly detection — alerts if productivity deviates >50% from team average (above or below)

## 8.6 AI Development Timeline — Week by Week

| Period | AI Development Activity |
| --- | --- |
| May 4–7 (Week 1) | GPU cloud instances set up; MLflow experiment tracking configured; Label Studio deployed; labeling guidelines written |
| May 4–21 (Pilot phase) | Pilot photos labeled immediately — target 3,000 labeled images; Model 4 (QC checker) built and deployed for May 25 launch |
| May 25 – May 31 | Labeling team at full speed — target 15,000 labeled images; Model 1 first training run; Model 2 architecture designed |
| Jun 1–20 | Model 1 and Model 2 trained on full dataset; internal validation and accuracy testing; bug fixes and retraining |
| Jun 21–30 | Model 1 and Model 2 production deployment — integrated into data pipeline; accuracy validation on live data |
| Jul 1 – Aug 15 | Continuous retraining with growing labeled data (target 50,000+ by Aug 15); Model 3 architecture design and initial training |
| Aug 16 – Sep 15 | AI Dashboard integration — all model outputs displayed in dashboard; predictive maintenance module finalized |
| Sep 16–30 | MSEDCL UAT on AI Dashboard; MSEDCL IT team training on AI system; documentation and handover |

## 8.7 Data Labeling Strategy

| Parameter | Plan |
| --- | --- |
| Labeling Team Size | 4 full-time dedicated annotators (hired from May 4) |
| Labeling Tool | Label Studio — open source, self-hosted on cloud VM, no license cost |
| Daily Labeling Target | 500–600 images per day (team of 4) = ~3,000/week |
| Total Labeled Images Target | 3,000 by Apr 21 → 15,000 by May 31 → 50,000 by Aug 15 |
| Labeling Taxonomy | Pole type (6 classes) + Condition score (5 levels) + Defect tags (rust / crack / lean / damage) |
| Quality Control | 10% of each batch reviewed by AI Lead; inter-rater agreement target ≥ 85% |
| Labeling Guidelines Doc | Prepared in Week 1; updated after pilot with real field photo examples |
| Active Learning | From Month 3: AI selects hardest-to-classify images for human labeling — maximizes model improvement per label |

## 8.8 AI Infrastructure Requirements

| Component | Specification | Purpose |
| --- | --- | --- |
| GPU Training Instance | AWS p3.2xlarge or equiv. — NVIDIA V100 GPU, 61GB RAM | Model training runs |
| GPU Inference Instance | AWS g4dn.xlarge — NVIDIA T4 GPU, 16GB RAM | Real-time classification API |
| Label Studio VM | 4 vCPU, 8GB RAM, 500GB SSD | Labeling tool for 4 annotators |
| MLflow Tracking Server | 2 vCPU, 4GB RAM | Experiment tracking, model registry |
| Model Storage | S3 bucket dedicated for model artifacts | Model version storage |
| Inference API | FastAPI on Docker + Kubernetes | Production model serving, auto-scaling |
| AI Framework | TensorFlow 2.x + PyTorch | Model development and training |
| Model Architecture Base | EfficientNet-B3 (Type), YOLOv8 (Condition/Defect) | Transfer learning on pre-trained weights |

# Chapter 9: Manpower Planning

⚠ CRITICAL MANPOWER NOTE: Hiring begins May 4, 2026 (T0). There is NO pre-hired team. Mass hiring and training of ~160 field staff must complete within the first 3 weeks (May 4–21) in parallel with the pilot survey. This is the most time-critical HR activity of the entire project.

## 9.1 Organisation Structure

## 9.2 Complete Role Directory

### 9.2.1 Core Management & Leadership

| Role | Count | Resource Name | Qualification | Min. Experience | Key Responsibilities | Start Date |
| --- | --- | --- | --- | --- | --- | --- |
| Project Delivery Head | 1 | Suresh Mathur | BE/BTech / MBA Project Management | 8–10 years PM experience | End-to-end delivery; milestone tracking; resource management; escalation | May 4 |
| Resource Management Lead | 1 | Rutwik Sonar | Graduate + proven field leadership | 7+ years large-scale field ops | Manage all district field teams (Nagpur + C.S.N. Region); logistics; daily operations control | May 4 |
| Technical Lead | 1 | Mukesh Muthiyan | BTech/MCA/MSc IT or CS | 5+ years data management | Database integrity; data quality oversight; reporting pipeline | May 4 |
| AI Engineer Lead | 1 | Aatish Langhee | BTech/MTech CS with AI/ML specialization | 5+ years AI/ML, 2+ years lead role | AI strategy; system architecture; tech team leadership; MSEDCL tech interface | May 4 |
| GIS Specialist | 1 |  | BTech/MSc Geography / GIS / Geomatics | 4+ years GIS platforms | GIS platform management; spatial analysis; map layers; dashboard GIS layer, ArcGIS, ArcFM | May 4 |

### 9.2.2 Technology Team

| Role | Count |  | Qualification | Min. Experience | Key Responsibilities | Start Date |
| --- | --- | --- | --- | --- | --- | --- |
| Software Delivery Lead |  | Sharandeep Singh |  |  |  |  |
| Senior Backend Developer - Vaibhav | 3 | Vaibhav Shubham Prajwal | BTech CS / MCA | 4+ years Python/Node.js, REST API, PostgreSQL | API development; database schema; cloud infrastructure; pipeline | May 4 |
| Mobile App Developer (Android & iOS) | 2 | Adarsh | BTech CS | 3+ years React Native or Flutter, offline-first apps | Survey app development; GPS/camera features; offline sync; QR scanning | May 4 |
| AI / ML Engineer | 5 | Atharva Anurag Aditi Tushar | BTech/MTech CS with ML/CV specialization | 3+ years ML, computer vision, TensorFlow/PyTorch | Model development; training pipelines; inference deployment; monitoring | May 4 |
| Data Engineer | 1 |  | BTech CS / MCA | 3+ years ETL, data pipelines, database optimization | ETL pipeline; data quality automation; database performance; export tools | May 4 |
| Frontend / Dashboard Developer | 3 | Sharandeep Yash Yogesh Swapnil | BTech CS | 3+ years React/Vue.js, GIS frontend (Leaflet/Mapbox) | AI dashboard development; GIS map frontend; charts and analytics UI | May 4 |
| DevOps / Cloud Engineer | 2 | Rushikesh Vrushabh | BTech CS | 3+ years AWS/Azure, Docker, Kubernetes, CI/CD | Infrastructure-as-code; CI/CD; monitoring setup; security; auto-scaling | May 4 |
| Data Labeling Annotators | 20 | College Interns | Any graduate; eye for detail; trainable | Training provided in Week 1 | Label training images for AI models; maintain labeling quality standards | May 4 |
| QA / Testing Engineer | 1 | Megha | BTech CS / BCA | 2+ years software testing (API + mobile) | Test app, APIs, data pipeline, AI outputs; regression testing; bug reporting | May 4 |

### 9.2.3 Field Team

| Role | Count | Qualification | Training Required | Key Responsibilities | Start Date |
| --- | --- | --- | --- | --- | --- |
| District Coordinator | 14 (1 per district) | Graduate; MS Office; Marathi + Hindi / English | 2-day orientation on app, reporting format, MSEDCL liaison protocol | Coordinate with local MSEDCL office; manage district surveyors; daily reporting to Field Ops Manager | May 8 |
| Field Supervisor / Team Leader | ~25 (1 per 5 surveyors) | Graduate; smartphone literacy; local area knowledge | 5-day training: app + QC review process + safety + SOP | Supervise 5 surveyors; perform 10% physical QC daily; approve/reject submissions; productivity tracking | May 42–19 |
| Field Surveyor | ~120 | 10th/12th pass minimum; smartphone literacy essential; physical fitness | 5-day intensive: app usage, GPS accuracy, pole identification, condition scoring, safety | Physical pole survey; GPS capture; mandatory 3-photo capture; data entry; UID marking on pole | May 25 |
| Drone Operator | 10–15 (via agency) | DGCA Remote Pilot License (RPLC) mandatory; commercial survey experience | Project-specific briefing on zone priority and cross-referencing with mobile data | Drone flights for forest/tribal/difficult zones; orthomosaic generation; pole detection support | May 1 |

### 9.2.4 Support Functions

| Role | Count | Qualification | Key Responsibilities | Start Date |
| --- | --- | --- | --- | --- |
| HR / Recruitment Coordinator | 1 | MBA HR / Graduate | Mass hiring coordination; onboarding ~160 field staff; attendance; replacement hiring throughout project | May 4 |
| Finance / Accounts Executive | 1 | BCom / MBA Finance | Budget tracking; vendor payments; travel reimbursements; monthly cost reporting | May 4 |
| Legal / Compliance Officer | 1 | LLB / Graduate | Drone permits; MSEDCL MoU; district permission letters; NDAs for all staff; compliance tracking | May 4 |
| Administrative Support | 2 | Graduate | Office management; logistics; device procurement; stationery and consumables | May 4 |
| IT Helpdesk / Support | 2 | BCA / Diploma IT | Device setup; app troubleshooting; remote field tech support; SIM management | May 4 |

## 9.3 Hiring Timeline — Critical Path

| Activity | Date | Output | Owner |
| --- | --- | --- | --- |
| Job postings live (all roles) | May 4, 2026 | Postings on Naukri, LinkedIn, college boards, WhatsApp job groups, employment exchanges | HR Coordinator |
| Core management team assembled | May 4, 2026 | Project Director, PM, Field Ops Mgr, AI/Tech Lead, Data Manager, GIS Specialist on board | Project Director |
| Tech team assembled | May 4, 2026 | All 15 tech team members on board; devices set up; coding environments ready | AI/Tech Lead |
| Support staff on board | May 4, 2026 | HR, Finance, Legal, Admin, IT Support (7 people) | Project Manager |
| District Coordinator selection (36) | May 4–7 | 14 coordinators selected — preference for local candidates with district knowledge | HR + Field Ops Manager |
| Supervisor + Surveyor interviews | May 4–7 | ~160 candidates shortlisted — ~25 supervisors + ~120 surveyors | HR Coordinator + Field Ops Mgr |
| Labeling team on board (4) | May 4 | 4 annotators start labeling pilot photos from Day 1 | AI Engineer Lead |
| Training Batch 1 (180 pax) | May 8–12 | Supervisors for 7 districts + Surveyors Batch 1 trained and certified | Field Ops Manager |
| Training Batch 2 (180 pax) | May 45–19 | Remaining supervisors + Surveyors Batch 2 trained; all devices distributed | Field Ops Manager |
| Full deployment Day | May 25, 2026 | ALL ~120 surveyors + ~25 supervisors active in their districts | Project Manager |

## 9.4 Recruitment Strategy

### Surveyor Recruitment (~120 — Volume Hiring in 7 Days)

- Primary channel: ITI / Polytechnic colleges in all 5 regions — local candidates strongly preferred

- Secondary channel: District employment exchanges — candidates with basic technical background

- Tertiary channel: Retired MSEDCL linemen / helpers — invaluable field knowledge, fast learners

- WhatsApp job groups per district — spreads quickly through local networks

- Contract-based engagement: 6-month contract aligned with project end date (May 25 – November 3)

- Selection criteria: Smartphone literacy (mandatory), physical fitness, local area familiarity, basic reading/writing

### Technical / Management Roles

- Naukri.com and LinkedIn for all technology and management roles

- Engineering college placement cells — Pune, Nagpur, Mumbai, Nashik for fresh talent

- Contract / freelance arrangement for data labelers and junior support roles

## 9.5 Training Program — 5-Day Module

| Day | Module | Duration | Target Audience | Content |
| --- | --- | --- | --- | --- |
| Day 1 | App & GPS Training | 8 hours | All Surveyors + Supervisors | App installation and navigation; GPS accuracy; form filling; UID system; photo guidelines; submission workflow |
| Day 2 | Pole Identification & Scoring | 8 hours | All Surveyors + Supervisors | Types of poles (CC/Steel/Wood/Tubular); condition scoring 1–5; equipment identification; common field errors |
| Day 3 | Field Safety & Protocol | 8 hours | All Surveyors + Supervisors | Electrical safety distances; never-approach rules near live lines; PPE use; emergency protocol; buddy system |
| Day 4 | Mock Field Survey | Full day | All Surveyors + Supervisors | Supervised practice: 30–40 real poles surveyed under trainer observation; data reviewed live on dashboard |
| Day 5 | QC, Reporting & SOP | 8 hours | Supervisors only (extra module); Surveyors do app practice | Supervisor QC workflow; rejection criteria; daily reporting format; escalation protocol; AI output interpretation |

## 9.6 Safety & Personnel Policy

- Group accident insurance: Mandatory for all ~160 field staff from Day 1 of deployment

- PPE provided to every surveyor: Reflective safety jacket, helmet, gloves, ID card holder

- Electrical safety rule: Minimum 2-metre distance from any energized line — strictly enforced

- Buddy system: No surveyor works alone in remote areas; minimum 2 people per team

- First aid kit: 1 kit per field vehicle; all supervisors briefed on basic first aid

- Emergency contact tree: Supervisor → District Coordinator → Field Ops Manager — max 30-minute response

- Incident reporting: Any safety incident reported within 1 hour; formal report within 24 hours

# Chapter 10: Infrastructure & Logistics

## 10.1 Infrastructure Overview

Given the 6-month timeline, all infrastructure must be procured and ready by May 4, 2026. There is no ramp-up time for equipment. All devices must be purchased, configured, and distributed before the pilot begins. Vendor contracts for vehicles and drones must be signed in the week before May 4.

## 10.2 Field Devices & Accessories — Complete List

| Device / Item | Qty | Specification | Purpose | Est. Unit Cost (₹) |
| --- | --- | --- | --- | --- |
| Android Smartphones | ~160 (~120 surveyors + ~25 supervisors) | Min 6.5" display, 64GB, 13MP camera, Android 11+, IP52 rated, 5000mAh battery | Primary field survey tool — app, GPS, photos | 12,000–18,000 |
| Spare Smartphones | 40 (10% buffer) | Same spec as above — field replacements | Immediate swap for broken/lost devices | 12,000–18,000 |
| Power Banks (20,000 mAh) | 400 (1 per field staff + spares) | Fast-charge 20,000 mAh; 2 USB-A + 1 USB-C output | Full-day battery backup for 8+ hour field use | 1,800–2,500 |
| GPU Workstations (AI Dev) | 2 | NVIDIA RTX 4080/A4000 GPU; 32GB RAM; 1TB NVMe SSD | On-premise AI model development and testing | 1,40,000–1,80,000 |
| Dedicated On-Prem Server | 1 | Dell PowerEdge or HP ProLiant; 2×CPU; 64GB RAM; 4TB RAID storage | Local backup server; dev environment; database mirror | 2,50,000–3,50,000 |
| NAS Storage (30TB) | 1 | QNAP or Synology NAS; RAID 6; 30TB usable storage | Central photo storage backup; large dataset archive | 2,00,000–2,80,000 |
| UPS (10 KVA) | 1 | APC/Eaton 10KVA UPS with 4-hour runtime for server room | Power continuity for HQ critical infrastructure | 1,20,000–1,60,000 |
| 5G Portable WiFi Routers | 70 (1 per supervisor + spares) | Dual SIM 5G; 10-device simultaneous connection; 12hr battery | Team field internet; sync in areas without personal data | 3,500–5,000 |
| Label Printers (UID Tags) | 5 | Brother/Zebra thermal label printer; 20mm width labels | Print QR + UID label stickers for pole tagging | 8,000–15,000 |
| UID Label Rolls (QR sticker) | 50,000 labels | Weatherproof UV-resistant adhesive; 50mm × 30mm size | Physical UID tagging on poles (accessible poles) | ~₹5/label |
| Safety Kit per Field Staff | 360 kits | Reflective vest (ANSI Class 2), hard hat, work gloves, safety boots voucher, ID holder | Field safety compliance — mandatory PPE | 1,500–2,500 |
| First Aid Kits | 70 (1 per field vehicle) | Standard burn + wound + fracture first aid kit | Field medical emergency preparedness | 800–1,200 |
| Measuring Tools | 70 sets | 5m steel retractable tape + spirit level for lean measurement | Pole height estimation and tilt measurement | 400–600 |
| Office Network Infrastructure | 1 setup | Gigabit managed switch; WiFi 6 APs (3); firewall; enterprise router | HQ office connectivity for 25-person team | 1,80,000–2,50,000 |
| Office Furniture — HQ | 1 setup | Desks, ergonomic chairs, storage cabinets, conference table, whiteboards for 25 staff | Core HQ workspace | 3,50,000–5,00,000 |

## 10.3 Vehicles & Transportation

| Vehicle Type | Qty | Purpose | Arrangement | Est. Monthly Cost |
| --- | --- | --- | --- | --- |
| Motorcycle / 2-Wheeler | ~150 (shared; 1 per 2 surveyors) | Primary movement in rural/narrow-access areas — most efficient for pole-to-pole survey | Surveyor own vehicle + fuel reimbursement; or project-hired for remote districts | ₹2,000–3,500 fuel/surveyor |
| SUV / Bolero 4WD | 60 (1 per supervisor team) | Team transport for 5 surveyors + supervisor + equipment; essential for semi-arid and rocky terrain | Monthly vehicle hire with dedicated driver from approved vendor | ₹25,000–35,000/vehicle |
| Drone Operations Vehicle | 5 (agency-provided) | Dedicated transport for drone team + equipment; equipment storage overnight | Included in drone agency contract | Covered in agency contract |

## 10.4 Office Infrastructure

### 10.4.1 Central Project HQ

| Item | Specification | Qty | Purpose |
| --- | --- | --- | --- |
| HQ Office Space | Min. 2,000 sq. ft., centrally located — Pune or Nagpur preferred | 1 | Core team of 25 — management, tech, AI, data, support |
| Meeting / War Room | 10-person capacity; 65" display / projector; video conferencing setup | 1 | MSEDCL presentations; daily management calls; crisis management |
| Server Room | Minimum 200 sq. ft.; AC; fire suppression; controlled access; UPS connected | 1 | On-prem server, NAS, UPS, network hardware |
| Dev Workstations | 25 total desks with dual-monitor setup (Dell/HP 24-inch monitors) | 25 | Tech team + management + data team workspace |

### 10.4.2 District Field Offices (14)

| Item | Specification | Qty |
| --- | --- | --- |
| Office Space (Rented) | 150–300 sq. ft.; near MSEDCL divisional office; ideally same building or adjacent | 14 (activated in district waves) |
| Basic Furniture | 2 desks; 4 chairs; 1 whiteboard for daily briefing | 14 sets |
| Internet Connection | Broadband + 4G router backup for daily report sync | 14 |
| Charging Station | Multi-port USB charging hub (10 ports) for overnight device charging | 1 per district |
| District Notice Board | Printed district zone map; daily targets; SOP checklists | 1 per district |

## 10.5 Drone Operations — Agency Selection

### Minimum Requirements for Drone Agency

- DGCA-registered operator with valid approvals for commercial survey operations

- Minimum fleet: 5 operational drones — DJI Matrice 300 RTK or Phantom 4 RTK or equivalent

- All pilots must hold valid DGCA Remote Pilot License Certificate (RPLC)

- Proven experience in infrastructure / utility sector drone surveys

- Photogrammetry capability — orthomosaic generation, point cloud processing (Pix4D / DroneDeploy)

- Ability to deploy across multiple districts simultaneously with 48-hour mobilization notice

- SLA: Each drone covers minimum 500 acres per day (at 60m altitude, 70% overlap)

| Vendor Tier | Type | Evaluation Criteria | Selection Process |
| --- | --- | --- | --- |
| Tier 1 — Primary | Full-service national drone survey companies (ideaForge, Drona Maps, Garuda Aerospace, Asteria) | DGCA certifications, fleet size, Maharashtra experience, SLA, pricing, data processing capability | RFP / Tender — issue by May 4; contract by May 45 |
| Tier 2 — Regional | Maharashtra-based DGCA-registered operators in Pune / Nagpur / Aurangabad | Quick mobilization, local area knowledge, cost efficiency, minimum fleet of 2 drones | Empanelment after Tier 1 contract — regional backup |

## 10.6 Annual Maintenance Contracts (AMC)

| Asset | AMC Type | Coverage | Est. Cost |
| --- | --- | --- | --- |
| Smartphones — 400 units | Comprehensive with screen + battery replacement | Accidental damage, battery degradation, screen | To Be Finalized |
| Supervisor Laptops — 60 units | On-site next-business-day service | Hardware failure, battery, keyboard, display | To Be Finalized |
| Tech Team Laptops — 20 units | On-site next-business-day premium service | Full hardware coverage + loaner device SLA | To Be Finalized |
| Servers + NAS (On-prem) | 24×7 on-site hardware AMC (ProSupport level) | Hardware failure, parts, on-site engineer, 4-hr SLA | To Be Finalized |
| GPU Workstations — 2 units | Comprehensive hardware AMC | GPU, CPU, RAM, storage failure | To Be Finalized |
| Drone Fleet | Included in drone agency SLA contract | Drone crash / malfunction / sensor replacement | Covered in agency contract |
| Office UPS | Annual preventive maintenance + battery check | Inverter + batteries + load test | To Be Finalized |
| Cloud Infrastructure | Managed by cloud provider under their SLA | 99.99% uptime SLA; no separate AMC needed | Included in cloud cost |

## 10.7 Communication Infrastructure

- WhatsApp Groups (structured hierarchy): All-India Management → Circle-wise → District-wise → Individual team groups

- Project Management Tool: Jira or ClickUp — all tasks, milestones, and issue tracking; mandatory for all roles

- Video Conferencing: Google Meet / MS Teams — daily 15-minute stand-up for management; weekly district coordinator calls

- Official Project Email: All formal communication via project domain email — not personal IDs

- SIM Cards: Each of 400 field devices provided with Jio/Airtel enterprise SIM; 5GB/day data plan

- Emergency Hotline: Dedicated project helpline number for field emergencies — monitored 07:00–20:00 daily

# Chapter 11: Budget Framework

## 11.1 Budget Notes & Assumptions

★ BUDGET BASIS: Planning-stage estimates for a 6-month project (May 4 – November 3, 2026). All human resource / salary costs are marked 'To Be Verified' per MSEDCL HR policy. Final figures to be confirmed after: (a) MSEDCL scope approval, (b) pilot actuals, (c) formal vendor RFP/tender responses. Device costs based on Maharashtra market rates (Q1 2026). Field operations costs based on 6-month project duration.

## 11.2 Capital Expenditure (CapEx) — One-Time Procurement

### A. Field & Office Devices

| Item | Qty | Unit Cost (₹) | Total (₹) | Notes |
| --- | --- | --- | --- | --- |
| Android Smartphones (Survey+Supervisor) | 400 | 15,000 | 60,00,000 | Including 40 spares at same spec |
| Power Banks (20,000 mAh) | 400 | 2,200 | 8,80,000 | 1 per field device |
| Ruggedized Phone Cases | 400 | 650 | 2,60,000 | Military-grade shockproof |
| Supervisor Laptops | 60 | 52,000 | 31,20,000 | i5, 8GB, 256GB SSD |
| Tech Team Laptops | 20 | 80,000 | 16,00,000 | i7, 16GB, 512GB SSD |
| GPU Workstations (AI Dev) | 2 | 1,60,000 | 3,20,000 | RTX 4080 / A4000 GPU |
| On-Prem Backup Server | 1 | 3,00,000 | 3,00,000 | Dell/HP enterprise server |
| NAS Storage (30TB) | 1 | 2,40,000 | 2,40,000 | QNAP/Synology RAID 6 |
| UPS 10 KVA | 1 | 1,40,000 | 1,40,000 | APC/Eaton with 4-hr runtime |
| 5G Portable WiFi Routers | 70 | 4,500 | 3,15,000 | Dual SIM, 10 devices |
| Label Printers (UID tags) | 5 | 12,000 | 60,000 | Thermal, weatherproof labels |
| UID Label Rolls (weatherproof) | 50,000 pcs | 5 | 2,50,000 | QR sticker + UID text |
| Safety Kits (complete per person) | 360 | 2,000 | 7,20,000 | Vest, helmet, gloves, ID holder |
| First Aid Kits | 70 | 1,000 | 70,000 | One per vehicle |
| Measuring Tools (tape + level) | 70 sets | 500 | 35,000 | Pole height estimation |
| Office Network Infrastructure | 1 setup | 2,20,000 | 2,20,000 | Switch, WiFi AP, firewall, router |
| Office Furniture (25-person HQ) | 1 setup | 4,50,000 | 4,50,000 | Desks, chairs, cabinets, boards |
| SUB-TOTAL — DEVICES & EQUIPMENT |  |  | ~₹1,49,80,000 | Subject to bulk purchase discount |

### B. Technology Development (CapEx)

| Item | Basis | Estimated Cost (₹) |
| --- | --- | --- |
| Mobile Survey App (Android) | Custom dev — React Native/Flutter; offline-first; 3-month dev effort | To Be Finalized |
| Backend API + Cloud Setup | FastAPI + PostgreSQL/PostGIS; initial cloud architecture config | To Be Finalized |
| GIS Platform Setup | GeoServer setup; base map layers; tile styling; WMS/WFS config | 5,00,000–8,00,000 |
| AI/ML Platform Setup | GPU cloud instances; MLflow; Label Studio; training pipeline | To Be Finalized |
| AI Dashboard Development | Full React frontend; GIS integration; all 10 modules (see Ch.5) | To Be Finalized |
| System Integration & UAT | End-to-end testing; MSEDCL UAT; bug fixes | To Be Finalized |
| SUB-TOTAL — TECH DEV (APPROX.) |  | ₹25,00,000–50,00,000 (estimate) |

## 11.3 Operational Expenditure (OpEx) — 6 Months

### A. Cloud & Software Costs

| Item | Basis | Monthly Cost (₹) | 6-Month Total (₹) |
| --- | --- | --- | --- |
| Cloud Hosting (App + DB + API) | 2–4 production VMs; autoscaling for 300 device syncs | To Be Finalized | To Be Finalized |
| Cloud Storage (Photos) | Estimated 200–300TB over 6 months; ~3 photos × 3MB × 70 lakh poles | To Be Finalized | To Be Finalized |
| GPU Cloud (AI Training) | ~200 GPU hours/month during training; spot instances used | To Be Finalized | To Be Finalized |
| SIM Cards + Data Plans (400 devices) | Jio/Airtel enterprise plan; 5GB/day; 400 SIMs | ~8,00,000 | ~48,00,000 |
| GIS / Map Service (Mapbox) | Commercial API plan for dashboard tile serving | ~50,000 | ~3,00,000 |
| Project Management Tool (Jira) | Cloud license for 50 users | ~20,000 | ~1,20,000 |
| Video Conferencing (Teams/Meet) | Enterprise plan for 50 users | ~10,000 | ~60,000 |
| Antivirus / Security Software | Endpoint protection for 80 devices (laptops + workstations) | ~15,000 | ~90,000 |
| SUB-TOTAL (known items) |  | ~8,95,000+ | ~53,70,000+ |

### B. Field Operations Costs

| Item | Basis | Total Cost for 6 Months (₹) |
| --- | --- | --- |
| SUV/Bolero Hire (~25 vehicles) | ₹30,000/vehicle/month × 25 × 5.5 months (May 25–Nov 3) | ~₹41,25,000 |
| Fuel Reimbursement (2-wheelers) | ₹2,500/surveyor/month × 120 × 5 months | ~₹15,00,000 |
| District Office Rent (36 offices) | ₹10,000/month × 14 offices × avg 5 months | ~₹7,00,000 |
| Drone Agency Contract | Per district; per flight hour; orthomosaic processing — subject to RFP | To Be Finalized via RFP |
| Field Consumables & Printing | UID tags, permanent markers, stationery, printing — per month | ~₹1,50,000 (total) |
| Travel & Accommodation | Inter-district management travel; hotel for training batches | To Be Finalized |
| Vehicle Driver Cost | Drivers for ~25 vehicles — included in vehicle hire rate or separate | Included in hire rate or TBF |
| SUB-TOTAL FIELD OPS (known) |  | ~₹64,75,000+ (excl. drone & travel) |

### C. Human Resource Costs

| Role / Category | Count | Duration (Months) | Monthly Cost | Total Cost |
| --- | --- | --- | --- | --- |
| Project Director / Nodal Officer | 1 | 6 | To Be Verified | To Be Verified |
| Project Manager | 1 | 6 | To Be Verified | To Be Verified |
| Field Operations Manager | 1 | 6 | To Be Verified | To Be Verified |
| Data Management Manager | 1 | 6 | To Be Verified | To Be Verified |
| AI / Technology Lead | 1 | 6 | To Be Verified | To Be Verified |
| GIS Specialist | 1 | 6 | To Be Verified | To Be Verified |
| Backend Developers | 2 | 6 | To Be Verified | To Be Verified |
| Mobile App Developers | 2 | 6 | To Be Verified | To Be Verified |
| AI / ML Engineers | 3 | 6 | To Be Verified | To Be Verified |
| Data Engineer | 1 | 6 | To Be Verified | To Be Verified |
| Frontend / Dashboard Developer | 1 | 6 | To Be Verified | To Be Verified |
| DevOps / Cloud Engineer | 1 | 6 | To Be Verified | To Be Verified |
| Data Labeling Annotators | 4 | 6 | To Be Verified | To Be Verified |
| QA / Testing Engineer | 1 | 6 | To Be Verified | To Be Verified |
| District Coordinators | 14 | ~5 months | To Be Verified | To Be Verified |
| Field Supervisors | ~25 | ~5.5 months | To Be Verified | To Be Verified |
| Field Surveyors | ~120 | 5 months (May 25 – Nov 3) | To Be Verified | To Be Verified |
| Drone Operators (via agency) | 10–15 | Per contract | Included in agency | Per agency contract |
| Support Staff (7 roles) | 7 | 6 | To Be Verified | To Be Verified |
| TOTAL HR |  |  | To Be Verified | To Be Verified |

## 11.4 Budget Summary

| Budget Head | Estimated Amount (₹) | Status |
| --- | --- | --- |
| A. Devices & Equipment (CapEx) | ~₹1,49,80,000 | Based on Q1 2026 market rates |
| B. Technology Development (CapEx) | ₹25,00,000–50,00,000 | Estimate; finalize after scope confirmation |
| C. Cloud & Software (OpEx — 6 months) | ₹53,70,000+ (known items) | Cloud costs TBF after architecture sizing |
| D. Field Operations (OpEx — 6 months) | ₹64,75,000+ (known items) | Drone agency + travel TBF via RFP |
| E. Human Resources (6 months) | To Be Verified | Per MSEDCL / project HR policy |
| F. Permissions & Legal | ₹10,00,000–15,00,000 | Drone permits, MoU, NDAs, district letters |
| G. Training & Capacity Building | ₹10,00,000–15,00,000 | Training materials, venues, field kits, refreshments |
| H. Contingency Reserve (10%) | 10% of A+B+C+D | Buffer for unforeseen field / tech expenses |
| GRAND TOTAL (excl. HR & TBF items) | ~₹4,50,00,000–5,50,00,000+ | HR costs to be added post HR policy confirmation |
| ⚠ NOTE: The budget above reflects a 6-month compressed project. All salary/HR figures require formal HR policy verification. Drone agency costs will be determined via RFP (to be issued May 4). Cloud storage costs will be finalized once data volume estimates are confirmed during the pilot (May 4–21). |  |  |

# Chapter 12: Permissions, Licensing & Legal Framework

⚠ PERMISSION URGENCY: Given the 6-month timeline, ALL permissions must be initiated BEFORE May 4, 2026 where possible. Especially drone permits (DGCA) require 4–8 weeks processing time. Delays in permissions will directly delay field operations.

## 12.1 MSEDCL Internal Authorizations

| Authorization | From | Purpose | Required By |
| --- | --- | --- | --- |
| Project Sanction / Work Order | MSEDCL Board / CMD | Official project sanction — foundation for all other approvals | Pre May 4 (completed before T0) |
| Data Access Authorization | MSEDCL IT / CTO | Access to existing GIS, network maps, SCADA integration | May 4 (T0) |
| Circle-wise Co-operation Circular | MSEDCL HQ (per circle) | Mandatory directive to all divisional offices to cooperate with survey teams | May 4 (issued before pilot) |
| Employee / Asset Access Letter | MSEDCL Field Division | Access to MSEDCL premises, substations, infrastructure access | Before each district start |
| Data Confidentiality Agreement | MSEDCL Legal | Protect MSEDCL's data; define ownership; restrict unauthorized sharing | May 4 (all team members) |
| MoU / Contract Agreement | MSEDCL Procurement / Legal | Formal contract defining scope, deliverables, timelines, payment | Pre May 4 |

## 12.2 Drone / UAV Regulatory Approvals — DGCA

| Requirement | Details | Processing Time | Action Required |
| --- | --- | --- | --- |
| Unique Identification Number (UIN) | Each drone registered on DGCA DigitalSky portal | 2–4 weeks | Drone agency to file before May 4 |
| Remote Pilot License (RPLC) | Every pilot must hold valid DGCA RPLC for Medium category | 4–8 weeks | Agency must have certified pilots already |
| NPNT Compliance | No Permission No Takeoff — all drones must be NPNT hardware/software compliant | Device-level requirement | Confirm with agency at procurement stage |
| Green Zone Flights | Most rural/agricultural areas — no prior permission; NPNT compliance sufficient | Real-time per flight | Agency manages via DigitalSky app |
| Yellow Zone Permission | Within 8–12 km of airports (Nagpur, Nashik, Aurangabad etc.) | 48–72 hours per flight plan | Agency submits in advance — part of mission planning |
| Red Zone Restriction | Near military zones, strategic infra — NO FLY | Not permitted | Survey team avoids; ground survey only |
| Security Clearance (Gadchiroli / border) | DGCA + MHA clearance for sensitive LWE / border areas | 4–12 weeks | Legal officer to file by May 4 — critical path item |

## 12.3 State / District Level Permissions

| Permission | From | Purpose | Timeline |
| --- | --- | --- | --- |
| District Survey Intimation Letter | District Collector / SP Office | Informs administration of survey activity; prevents team being stopped by police | 2 weeks before each district activation |
| Police Intimation | Superintendent of Police (SP) | Field teams carry SP letter; solves >90% of on-ground questioning by authorities | One-time per district; filed by District Coordinator |
| Forest Department Permission | Divisional Forest Officer (DFO) | Mandatory for survey in reserved / protected forest areas (Gadchiroli, Chandrapur, Palghar) | Apply by May 4 — 4–6 week processing |
| Tribal Area Entry Permit (ITR) | District Collector (tribal districts) | Required in Scheduled Area tribal districts for non-tribal entry | Apply early — coordinate through MSEDCL |
| Revenue Dept. Intimation | Tehsildar (rural areas) | Village-level access for agricultural land poles | Informal coordination + Collector letter sufficient |
| Cantonment Area Clearance | Local Military Authority | Required in Pune, Nagpur, Aurangabad cantonment areas | Through MoD — apply via MSEDCL formal channel |

## 12.4 Data Privacy & Security Compliance

- Pole infrastructure data is NOT personal data under DPDPA 2023 — no consent needed for pole records

- All cloud storage must be India-based data centers (data residency compliance for government-adjacent project)

- Photo metadata (GPS-tagged) must be stored securely — restricted access only

- All project team members sign NDA before Day 1 — covers data confidentiality and non-disclosure

- Field surveyor location tracking data: Consent obtained at contract signing (DPDPA compliance)

- Data sharing with any third party requires explicit written MSEDCL authorization in advance

## 12.5 Permission Timeline Tracker

| Permission | Filed By | Target Date | Status |
| --- | --- | --- | --- |
| MSEDCL Board Project Sanction | Project Director | Pre May 4 | To Be Confirmed |
| MoU / Work Order Execution | Legal Officer + PM | Pre May 4 | To Be Confirmed |
| DGCA Drone UIN (all drones) | Drone Agency | Pre May 4 (critical!) | Pending — Agency to confirm |
| MSEDCL Circle Co-operation Circular | MSEDCL Nodal Officer | May 4 (Day 1) | To Be Issued |
| Forest Dept. (Gadchiroli / Chandrapur) | Legal Officer | May 4 (filing) | Pending — 4–6 week lead time |
| Tribal Area Entry (applicable districts) | Legal + MSEDCL | May 4 (filing) | Pending — Early filing critical |
| Pilot District — Nashik Collector Letter | District Coordinator (Nashik) | May 4 | Pending |
| All 14 Districts — SP Letters | Legal + 14 Coordinators | Staggered with district activation | Ongoing |
| Security Clearance (LWE districts) | Legal Officer + MSEDCL | May 4 filing — starts ASAP | Pending — 4–12 weeks |
| NDA — All Staff (360+) | HR + Legal | May 4 onward (all hires) | Ongoing from T0 |

# Chapter 13: Risk Management

## 13.1 Risk Context — 6-Month Compressed Timeline

With a 6-month timeline and zero recovery buffer, risk management is not optional — it is a core operational discipline. The project has no room for extended disruptions. Every high-severity risk has a pre-prepared mitigation and a clear escalation owner. Risks are monitored weekly by the Project Manager and reviewed monthly by the Project Director.

## 13.2 Risk Register

| Risk ID | Risk | Category | Severity | Probability | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| R01 | MSEDCL field staff non-cooperation at divisional level | Operations | CRITICAL | Medium | MSEDCL Board circular before T0; Project Director personally brief Circle SEs; escalation path pre-defined |
| R02 | Mass surveyor hiring failure — cannot onboard 300 in 3 weeks | HR | CRITICAL | Medium | Hiring campaign before May 4; pre-screen candidates; use multiple channels; hire 10% buffer (330 not 300) |
| R03 | Drone DGCA permissions delayed — forest districts uncoverable | Regulatory | HIGH | Medium-High | File ALL drone permits before May 4; start with non-drone areas first; ground survey fallback for delay |
| R04 | Poor 4G connectivity in remote districts — sync failures | Technology | HIGH | High | Offline-first app design; local SQLite storage; surveyors sync at district office daily; no data loss possible |
| R05 | High surveyor attrition in summer heat (May–June) | HR | HIGH | High | Contract with performance bonus at 3-month mark; 30-person replacement bench always maintained; rotate districts |
| R06 | Mobile app critical bugs affecting field productivity | Technology | HIGH | Medium | 2-week intensive QA before pilot; pilot as final UAT; hotfix deployment pipeline active from Day 1 |
| R07 | Data security breach — pole location data exposed | Security | HIGH | Low | RBAC + JWT auth; encrypted data in transit + at rest; penetration test in Month 1; no public access |
| R08 | AI model accuracy below 85% threshold at June 30 deadline | Technology | HIGH | Medium | Parallel labeling from Day 1; active learning for efficient labeling; human fallback for low-confidence records |
| R09 | Monsoon disruption to field operations (June–July) | External | HIGH | High | Maharashtra monsoon is predictable — schedule coastal/Konkan area surveys in May–May; Vidarbha for July |
| R10 | Budget overrun due to unforeseen field costs | Financial | HIGH | Medium | Pilot actuals (May 4–21) provide real cost baseline; 10% contingency buffer; weekly cost tracking vs. budget |
| R11 | Field safety incident — surveyor injury near live line | Safety | CRITICAL | Low-Medium | Mandatory electrical safety training Day 3; buddy system; no-approach rule; group accident insurance; supervisor spot-checks |
| R12 | Duplicate or poor-quality data entering database at scale | Data Quality | HIGH | Medium | AI QC Model 4 live from May 25; real-time GPS duplicate detection; 10% physical verification by supervisors |
| R13 | Drone agency fails to deliver — missed forest area coverage | Vendor | HIGH | Medium | Two agencies empanelled; minimum 30-day termination notice in contract; activation of Tier 2 within 48 hours |
| R14 | Scope additions by MSEDCL during project mid-flight | Scope | MEDIUM | Medium | MoU defines scope clearly; formal change request process; cost and timeline impact assessment before any approval |
| R15 | Cloud provider outage causing data access disruption | Technology | MEDIUM | Low | On-premise NAS mirror; daily automated export; multi-AZ cloud deployment; 4-hour RTO target |

## 13.3 Critical Risk Response Plans

### R01 — MSEDCL Non-Cooperation (CRITICAL)

The single greatest operational risk for this project. An uncooperative divisional office can freeze operations in an entire district. Pre-agreed escalation path: Surveyor issue → District Coordinator → Field Ops Manager (2 hours) → Project Manager (4 hours) → Project Director + MSEDCL Nodal Officer (same day). MSEDCL Board-level directive must name specific consequences for non-compliance. Project Director to do personal calls with all 15 Circle SEs in the week before T0.

### R02 — Mass Hiring in 3 Weeks (CRITICAL)

Hiring ~120 surveyors and ~25 supervisors in 7 days (May 4–7) with training completing May 21 is the tightest single execution challenge in the project. Mitigation: (1) Begin outreach and pre-screening before T0; (2) Use a structured shortlisting form — screen via WhatsApp first, then 15-minute interview; (3) Hire 10% buffer — ~132 surveyors, ~28 supervisors; (4) Keep a 'standby bench' of 25 pre-qualified replacements.

### R05 + R09 — Monsoon + Summer Attrition

Maharashtra's monsoon begins in Konkan around June 1 and reaches Vidarbha by June 15. This directly overlaps with the peak survey period. Mitigation: (1) Complete all Konkan coastal districts by May 31; (2) Target Vidarbha (Amravati, Akola, Yavatmal) in July when other issues are lower; (3) Provide monsoon gear (rain jacket) to all field staff; (4) Establish daily 'weather hold' decision authority with District Coordinator — do not force field work in unsafe conditions; (5) Summer bonus (small incentive) for completing May target to combat attrition.

### R11 — Field Safety Incidents (CRITICAL SEVERITY)

This is non-negotiable. A single fatality or serious injury will halt the project and have severe legal consequences. Requirements: (1) Zero-tolerance approach — any surveyor found violating electrical safety protocol is immediately suspended; (2) First safety stand-down on any incident — all field ops pause for 24 hours for investigation; (3) Group accident insurance covering ₹10 lakh medical + ₹25 lakh accidental death benefit per person from Day 1; (4) Supervisors check PPE compliance every morning before departure.

# Chapter 14: Standard Operating Procedures & Monitoring

## 14.1 Daily Operational Rhythms

### Surveyor — Daily SOP

| Time | Activity | Output |
| --- | --- | --- |
| 07:00 AM | Arrive at district base / meeting point; PPE inspection by supervisor | Attendance marked; PPE compliance confirmed |
| 07:15 AM | Morning briefing — today's zone on app; yesterday's issues reviewed; daily target confirmed | Zone downloaded; today's target visible on app |
| 07:30 AM | Depart to survey zone on motorcycle/vehicle | Travel to start point |
| 08:00 AM | Survey commences — first pole of the day | Survey records start populating |
| 12:00 PM | Mid-day sync check — confirm app is syncing; productivity update to supervisor via WhatsApp | Sync status: green; mid-day count reported |
| 01:00 PM | Break (60 minutes); charge phone via power bank | Device charging |
| 02:00 PM | Survey resumes | Afternoon survey |
| 04:30 PM | Return to base; force-sync all records; plug in device for charging | All day's records synced to cloud |
| 05:00 PM | End-of-day report in app: poles surveyed, issues, any unresolved records | Daily count submitted |
| 05:15 PM | Team debrief with supervisor; tomorrow's zone discussed | Next day's plan ready |

### Supervisor — Daily SOP

| Time | Activity |
| --- | --- |
| 06:30 AM | Review previous day's team records on supervisor dashboard; note any rejected/pending records |
| 07:00 AM | Conduct morning PPE + briefing for team of 5 surveyors; confirm zone assignments |
| 09:00 AM | Physical spot-check: visit 2 surveyors in field; verify GPS accuracy and data quality on 5–10 poles |
| 12:00 PM | Mid-day check-in call with all 5 surveyors; identify anyone behind target; dispatch support if needed |
| 12:30 PM | Submit mid-day progress to District Coordinator: team count, issues, any emergencies |
| 02:00 PM | Review and approve/reject morning's submissions on supervisor app |
| 04:00 PM | Afternoon field spot-check; look for quality issues in difficult terrain zones |
| 05:00 PM | All submissions reviewed; rejections sent back with clear correction instruction |
| 05:30 PM | End-of-day report to District Coordinator: total approved poles, productivity score, issues, tomorrow's plan |

### District Coordinator — Daily SOP

- 07:00 AM: Review all supervisors' end-of-previous-day reports; note district productivity vs. target

- 08:00 AM: Submit district morning status to Field Ops Manager on WhatsApp group

- 09:00 AM: Coordinate with local MSEDCL divisional office on any access or cooperation issues

- 12:00 PM: Mid-day productivity check — identify teams below 50% of daily target; escalate if needed

- 04:00 PM: Confirm all supervisors completed their mid-day reports

- 06:00 PM: Submit district daily summary: total poles surveyed today, cumulative, issues, tomorrow's plan

## 14.2 Data Management SOP

| Activity | Frequency | Responsible | Action Required |
| --- | --- | --- | --- |
| Sync verification | Daily 09:00 | Data Ops Team | Flag any device with >18 hours of unsynced records; alert District Coordinator |
| AI QC pipeline check | Daily 09:00 | AI/Data Team | Review AI QC Model 4 flags: GPS outliers, duplicates, photo failures; send corrections |
| Data completeness report | Daily | Automated + Data Manager | District-wise completeness score; follow up on records with <90% fields filled |
| Supervisor approval backlog | Daily | Data Manager | Flag districts where >200 records await supervisor approval for >24 hours |
| Database backup verification | Daily 23:00 | DevOps Engineer | Confirm daily automated backup completed; integrity check weekly |
| Weekly quality report | Every Monday | Data Manager | District-wise accuracy, completeness, productivity stats submitted to PM and MSEDCL Nodal Officer |
| Monthly QC audit (Level 4) | 1st of each month | Data Manager + AI Lead | Sample 500 records per district; manual cross-check; AI accuracy review; retraining trigger if needed |
| Drone validation cross-check | Post each drone sweep | Drone Team + Data Team | Compare drone-detected pole positions with mobile survey database; generate gap list for ground team |

## 14.3 AI System SOP

| Process | Trigger | Action | Owner |
| --- | --- | --- | --- |
| Real-time pole classification | Every sync event | Models 1 & 2 classify pole type and condition; result written to database | Automated (AI Engine) |
| Low confidence flag | Confidence score < 70% | Record flagged in dashboard as 'Needs Human Review'; data QC team reviews within 24 hours | Data QC Team |
| Model accuracy review | 1st of each month | Run full validation set through both models; compare to ground truth labels; calculate accuracy metrics | AI/ML Engineer |
| Retraining trigger | Accuracy drops below 85% | Initiate model retraining run with latest labeled dataset; test on validation set before promotion | AI Lead + ML Engineer |
| Model deployment | After retraining passes threshold | Blue-green deployment — zero downtime; old model serves until new passes health check | DevOps + AI Team |
| Labeling queue top-up | Daily 09:00 | Data Manager ensures labeling team has minimum 1,000 unlabeled images in Label Studio queue | Data Manager |
| Active learning selection | From Month 3 onwards | AI selects lowest-confidence records for human labeling — maximizes model improvement per label | Automated (MLflow integration) |
| Model version logging | Every deployment | Version, accuracy, training data size, date logged in MLflow Model Registry | AI/ML Engineer |

## 14.4 Monitoring Dashboard — Management View

### KPIs Visible in Real-Time

- Total poles surveyed across Maharashtra — live count and % of target

- District-wise progress — completion %, RAG status (Red <50%, Amber 50–85%, Green >85%)

- Daily productivity — avg poles per surveyor per day (today vs. target vs. project average)

- Data quality score — % records meeting all quality criteria (completeness + GPS + photos)

- AI pipeline status — records classified today, pending classification, flagged for human review

- Sync health map — devices with unsynced data >12 hours shown as red markers on map

- Critical poles alert — live count of poles rated Condition 5 (Critical) requiring immediate action

- Milestone tracker — % achievement vs. project timeline with projected completion date

## 14.5 Escalation Matrix

| Issue Level | Example | First Action | Escalate To | Resolution Target |
| --- | --- | --- | --- | --- |
| L1 — Minor | Surveyor confused about form field; app UI question | Self-resolve using SOP guide | Supervisor (if >1 hour) | Same day |
| L2 — Operational | GPS poor in area; surveyor sick; vehicle delayed | Supervisor resolves | District Coordinator (if >4 hours) | 24 hours |
| L3 — District | MSEDCL office uncooperative; drone permission blocked | District Coordinator + Field Ops Mgr | Project Manager | 48 hours |
| L4 — Project Critical | Safety incident; data breach; system failure; mass attrition | Project Manager immediate | Project Director + MSEDCL Nodal Officer | Immediate (<4 hours) |

## 14.6 Points of Contact (POC)

### Internal Project Team

| Role | Name | Responsibility | Contact Mode |
| --- | --- | --- | --- |
| Project Director | To Be Appointed | Final authority; MSEDCL board interface; critical decisions | Phone + Email (24/7 for emergencies) |
| Project Manager | To Be Appointed | Day-to-day coordination; all teams; milestone tracking | Phone + WhatsApp + Email |
| Field Operations Manager | To Be Appointed | All 14-district field teams; logistics; crisis management | Phone + WhatsApp (7 AM – 8 PM) |
| AI / Technology Lead | To Be Appointed | All technology; AI models; system issues; cloud | Email + Slack/Teams |
| Data Management Manager | To Be Appointed | Data quality; database; reporting; AI pipeline | Email + Slack/Teams |
| GIS Specialist | To Be Appointed | Map platform; spatial queries; dashboard GIS layer | Email + Slack/Teams |
| HR / Recruitment Coordinator | To Be Appointed | All hiring; onboarding; attendance; replacement hiring | Phone + WhatsApp |
| Legal / Compliance Officer | To Be Appointed | Permits; MSEDCL MoU; all legal matters | Phone + Email |
| District Coordinators (14) | To Be Appointed per District | District-level ops; MSEDCL liaison; team management | Phone + District WhatsApp group |

### External / MSEDCL Points of Contact

| Organisation | Designation | Responsibility | Contact Method |
| --- | --- | --- | --- |
| MSEDCL HQ | Nodal Officer (ED/SE level) | Project approvals; escalation; policy decisions | Phone + Formal letter |
| MSEDCL Circle (each) | Superintending Engineer (SE) | Circle-level access and cooperation | Phone + Email |
| MSEDCL Division (each) | Executive Engineer (EE) | Daily field access; sub-division cooperation | Phone |
| DGCA / DigitalSky | Regional ATC / helpdesk | Drone permits; NPNT compliance support | DigitalSky portal + helpline |
| Drone Agency | Agency Project Coordinator | Drone scheduling; flight logs; data delivery | Phone + Email + WhatsApp |
| Cloud Provider | Account Manager (AWS/Azure) | Cloud support; SLA issues; billing | Support portal + dedicated account manager |
| District Collector (each) | Nodal Officer | Survey permissions; police intimation support | Formal letter + phone |

## 14.7 Reporting Structure

| Report | Frequency | Prepared By | Submitted To | Key Content |
| --- | --- | --- | --- | --- |
| Daily Field Summary | Daily 6 PM | Each District Coordinator | Field Ops Manager | Poles surveyed, daily target vs. actual, issues, attendance |
| Weekly Progress Report | Every Monday | Project Manager | Project Director + MSEDCL Nodal Officer | All-district KPIs, AI status, financial summary, risks, decisions needed |
| Monthly Performance Report | 1st of each month | PM + Data Manager + AI Lead | MSEDCL Director / Management | Full KPI dashboard, budget vs. actuals, AI model performance, next month plan |
| Pilot Completion Report | May 25, 2026 | PM + AI Lead + Field Ops Mgr | MSEDCL Management | Pilot findings, per-pole cost actuals, SOP changes, full-deployment readiness confirmation |
| District Completion Report | On each district completion | District Coordinator + Data Manager | MSEDCL Circle SE + PM | District stats, quality scores, issues log, GIS map extract, handover checklist |
| AI Model Go-Live Report | June 30, 2026 | AI/Tech Lead | Project Director + MSEDCL | Model accuracy results, classification statistics, confidence distribution, known limitations |
| Final Project Report | November 3, 2026 | All Leads | MSEDCL CMD / Board | Full state survey results, AI system documentation, GIS deliverables, handover package, lessons learned |

# Chapter 15: Final Deliverables — November 3, 2026

★ ALL FIVE FINAL DELIVERABLES MUST BE COMPLETE AND HANDED TO MSEDCL BY SEPTEMBER 30, 2026 (1) Live GIS Dashboard (2) Complete Pole Database (3) AI System Operational (4) AI Dashboard with full features (5) Final Project Report

## D1 — Complete GIS Map of All Maharashtra Poles

| Attribute | Specification |
| --- | --- |
| Format | Web-based GIS map (browser-accessible) + Export formats: Shapefile (.shp), KML, GeoJSON, CSV |
| Geographic Coverage | Nagpur Region + C.S.N. Region of Maharashtra — 100% of surveyed poles plotted |
| Access Levels | Corporate (full state view) → Circle SE (circle view) → Division EE (division view) → Sub-division |
| Spatial Reference | WGS 84 (EPSG:4326) |
| Map Layers | Pole markers by type, Condition heat map, Risk zone overlay, District/Circle/Division boundaries, Drone-surveyed zones |
| Update Status | Live during project; static after handover (quarterly update plan to be agreed with MSEDCL) |
| Export Capability | On-demand export by geography, condition, type, date range — admin dashboard |
| Handover Date | Map live by August 31; final complete state by November 3, 2026 |

## D2 — Central Pole Asset Database

| Attribute | Specification |
| --- | --- |
| Database Platform | PostgreSQL 15 + PostGIS 3 — hosted on cloud (AWS/Azure/NIC) |
| Total Records | Estimated 55–75 Lakh pole records (1 record per unique pole) |
| Fields per Record | 30+ attributes: identity, location (GPS), physical, electrical, equipment, AI scores, photos, history |
| Photo Storage | Min. 3 photos per pole — cloud object storage; linked from DB by photo ID |
| Access API | Authenticated REST API — MSEDCL systems can query in real-time |
| Backup Policy | Daily automated backup; 30-day point-in-time recovery; secondary region mirror |
| Data Export | CSV, Excel, GIS formats on-demand from admin panel |
| Ownership | All data is MSEDCL property — credentials and ownership transferred November 3 |
| Handover Date | November 3, 2026 |

## D3 — AI System — Operational & Deployed

| AI Component | Description | Accuracy Target | Handover Date |
| --- | --- | --- | --- |
| Model 1: Pole Type Classifier | Classifies pole material type from photos — CC/Steel/Wooden/Tubular | ≥ 90% | June 30, 2026 (go-live); final Sept 30 |
| Model 2: Condition Assessor | Scores pole condition 1–5 from photos; localizes defects on image | ≥ 85% | June 30, 2026 (go-live); final Sept 30 |
| Model 3: Predictive Maintenance | Risk score per pole; maintenance priority list for next 12 months | Best-effort (data-dependent) | August 31, 2026 |
| Model 4: Data QC Checker | Real-time automated validation — GPS outliers, duplicates, photo quality | Real-time, rule-based | May 25, 2026 (live from Day 1 of full deploy) |
| Labeled Training Dataset | 50,000+ labeled pole images — owned by MSEDCL; permanent asset | N/A | November 3, 2026 |
| Full AI Documentation | Model cards, training data spec, API documentation, retraining guide | N/A | November 3, 2026 |

## D4 — AI Dashboard — MSEDCL Intelligence Interface

The AI Dashboard is the premium deliverable of the project — a fully web-based, role-accessible intelligence interface that MSEDCL management will use daily post-handover. It combines the GIS map, AI outputs, analytics, and operational tools in a single unified platform.

### Dashboard Feature Modules

| Module | Features |  | Available From |
| --- | --- | --- | --- |
| 1. Live Pole Map | Interactive GIS map; filter by district/circle/division/type/condition/risk; click any pole for full record + photos |  | August 31, 2026 |
| 2. District Progress Panel | Survey completion % per district; RAG status; daily update; target vs. actual bar chart |  | May 25, 2026 (internal); August 31 (MSEDCL) |
| 3. Condition Heat Map | Geographic distribution of condition scores across Maharashtra; zoom to any zone; identify regional degradation patterns |  | August 31, 2026 |
| 4. Priority Alert Board | Top 100 / 500 / 1,000 poles with Condition 5 (Critical) or 4 (Poor) — sorted by risk score; one-click work order export |  | August 31, 2026 |
| 5. AI Classification Panel | Breakdown of pole types state-wide; condition score distribution histogram; confidence score distribution |  | July 31, 2026 |
| 6. Predictive Maintenance Calendar | Month-by-month predicted maintenance requirements by district; export as maintenance plan |  | August 31, 2026 |
| 7. Analytics & Trends | Pole count by type/district/circle; condition trends; survey velocity charts; data quality over time |  | August 31, 2026 |
| 8. Custom Report Generator | User-configurable reports — select fields, filters, geography, date range; export to CSV / Excel / PDF |  | October 15, 2026 |
| 9. Drone Survey Overlay | Map layer showing drone-covered zones, detected pole positions, cross-referenced vs. ground survey |  | October 15, 2026 |
| 10. User & Access Management | MSEDCL role hierarchy management; add/remove users; set access levels (Corporate / Circle / Division) |  | November 3, 2026 |
| Dashboard Tech Specification |  | Detail |  |  |
| Frontend |  | React.js + Tailwind CSS — responsive (desktop + tablet) |  |  |
| GIS Layer |  | Leaflet.js + Mapbox GL JS — fast tile rendering for 70 lakh pole markers |  |  |
| Charts |  | Recharts / D3.js — interactive analytics |  |  |
| Backend API |  | FastAPI — all dashboard data served from central API with caching |  |  |
| Authentication |  | MSEDCL employee ID integration; role-based access control |  |  |
| Performance Target |  | Map loads full Maharashtra (all poles visible) within 5 seconds on standard broadband |  |  |
| Mobile Accessibility |  | Responsive design — usable on tablet for field supervisors |  |  |
| Training Provided |  | 3-day MSEDCL management training; 5-day MSEDCL IT admin training; recorded video tutorials |  |  |
| UAT |  | September 1–15, 2026 — MSEDCL UAT period with feedback integration |  |  |
| Final Handover |  | November 3, 2026 — credentials and admin access transferred to MSEDCL IT |  |  |

## D5 — Final Project Report

| Report Section | Content |
| --- | --- |
| Executive Summary | Project overview, key achievements, total poles surveyed, AI system performance summary |
| Survey Statistics | District-wise pole counts, type distribution, condition distribution, coverage verification |
| Technology Documentation | Full system architecture; API reference; database schema; deployment guide |
| AI System Documentation | Model cards (accuracy, training data, limitations); inference API docs; retraining guide |
| AI Dashboard Documentation | User manual for all 10 dashboard modules; admin guide; user management guide |
| Financial Summary | Actual vs. budgeted costs; per-pole cost actuals; cost breakdown by category |
| Lessons Learned | What worked, what was challenging, recommendations for Phase 2 / ongoing operations |
| Handover Checklist | All credentials, source code repositories, vendor contacts, SLA documents |
| MSEDCL Recommendations | Suggested next steps for Phase 2 (integration with SCADA/billing/complaint systems) |

Submission: November 3, 2026 — 3 bound hard copies + digital PDF to MSEDCL CMD, Director (Technical), and Nodal Officer

## 15.1 Deliverables Master Tracker

| Deliverable | Type | Target Date | Handover To |
| --- | --- | --- | --- |
| GIS Map — Live (full Maharashtra) | Web Application + Export Files | November 3, 2026 | MSEDCL IT / GIS Team |
| Central Pole Database | PostgreSQL + REST API + Credentials | November 3, 2026 | MSEDCL IT Team |
| AI Model 1 — Pole Type Classifier | Deployed API + Model Files + Docs | June 30, 2026 (go-live) | MSEDCL IT / AI Team |
| AI Model 2 — Condition Assessor | Deployed API + Model Files + Docs | June 30, 2026 (go-live) | MSEDCL IT / AI Team |
| AI Model 3 — Predictive Maintenance | Deployed API + Model Files + Docs | August 31, 2026 | MSEDCL IT / AI Team |
| AI Model 4 — Data QC Checker | Live pipeline component + Docs | May 25, 2026 (go-live) | MSEDCL IT Team |
| Labeled Training Dataset (50,000+ images) | Label Studio export + S3 bucket access | November 3, 2026 | MSEDCL IT / AI Team |
| AI Dashboard — All 10 Modules | Web Application + Admin + User Guide | November 3, 2026 | MSEDCL IT + Management |
| Mobile Survey App | Android APK + Source Code | November 3, 2026 | MSEDCL IT Team |
| Unique Pole ID System | Algorithm + Lookup API + Physical tags on poles | Ongoing; complete Nov 3 | MSEDCL Operations |
| Pilot Completion Report | PDF Report | May 25, 2026 | MSEDCL Management |
| Weekly Progress Reports (26 reports) | PDF / Digital | Every Monday throughout project | MSEDCL Nodal Officer |
| Monthly Performance Reports (6 reports) | PDF / Dashboard | 1st of each month | MSEDCL Director |
| District Completion Reports (36 reports) | PDF per district | Rolling as each district completes | MSEDCL Circle SE |
| AI Dashboard User Manual | PDF + Video Tutorials | October 20, 2026 | MSEDCL Management + IT |
| Full Technical Documentation | PDF Document Set | November 3, 2026 | MSEDCL IT Team |
| Final Project Report | Bound PDF + Digital (3 copies) | November 3, 2026 | MSEDCL CMD + Director + Nodal Officer |

# Appendices

## Appendix A: Glossary of Terms

| Term | Full Form / Meaning |
| --- | --- |
| MSEDCL | Maharashtra State Electricity Distribution Co. Ltd. |
| T0 | Project Start Date — May 4, 2026 |
| T6 | Project End Date — November 3, 2026 |
| GIS | Geographic Information System — digital mapping and spatial data platform |
| GPS | Global Positioning System — satellite-based location coordinates |
| UID | Unique Pole Identifier — permanent digital identity code per pole |
| AI / ML | Artificial Intelligence / Machine Learning |
| CNN | Convolutional Neural Network — type of AI model for image analysis |
| DGCA | Directorate General of Civil Aviation — India's aviation regulator |
| NPNT | No Permission No Takeoff — DGCA's mandatory digital drone clearance system |
| UAV | Unmanned Aerial Vehicle (Drone) |
| RPLC | Remote Pilot License Certificate — DGCA certification for drone pilots |
| API | Application Programming Interface — software communication protocol |
| LT | Low Tension — electrical lines below 1 kV (last-mile distribution) |
| HT | High Tension — electrical lines in 1–33 kV range |
| EHT | Extra High Tension — lines above 66 kV |
| PostGIS | Spatial extension for PostgreSQL — enables geographic/spatial queries |
| CapEx | Capital Expenditure — one-time asset investment |
| OpEx | Operational Expenditure — recurring ongoing cost |
| SOP | Standard Operating Procedure |
| POC | Point of Contact |
| RAG | Red-Amber-Green — traffic light status indicator in project management |
| MoU | Memorandum of Understanding — formal cooperation agreement |
| AMC | Annual Maintenance Contract |
| WGS 84 | World Geodetic System 1984 — universal GPS coordinate reference system |
| RFP | Request for Proposal — formal tender document for vendor selection |
| UAT | User Acceptance Testing — MSEDCL's formal testing of system before acceptance |
| ITI | Industrial Training Institute |
| DPDPA | Digital Personal Data Protection Act, 2023 |
| LWE | Left Wing Extremism — relevant for Gadchiroli / Chandrapur district security context |
| SE | Superintending Engineer — MSEDCL Circle-level senior officer |
| EE | Executive Engineer — MSEDCL Division-level officer |
| RBAC | Role-Based Access Control — security model for dashboard user permissions |

## Appendix B: 6-Month Master Timeline — Gantt Summary

| Activity | May 4–21 | May 25–May 31 | Jun 1–Jun 30 | Jul 1–Jul 31 | Aug 1–Aug 31 | Sep 1–Nov 3 |
| --- | --- | --- | --- | --- | --- | --- |
| PILOT (1 District) | ACTIVE | — | — | — | — | — |
| Mass Hiring & Training | ACTIVE | Replacements only | — | — | — | — |
| Full 36-District Survey | — | ACTIVE (START) | ACTIVE (PEAK) | ACTIVE | ACTIVE (CLOSE) | Gap fill only |
| App + Backend Development | Fixes + enhancements | Ongoing | Ongoing | Dashboard build | Dashboard UAT | Final fixes |
| AI Data Labeling | Pilot photos | Full speed | Full speed | Active learning | Wind down | Final dataset |
| AI Model Training & Deploy | Architecture | First training | MODELS LIVE | Refinement | Dashboard integration | Final |
| Drone Operations | Pilot cross-check | Forest zones | Forest zones | Validation sweeps | Final validation | Final aerial QC |
| GIS Map (Live) | — | Internal | Internal | Internal | MSEDCL access | Final state |
| AI Dashboard Build | — | — | Design | Build | Build + UAT | FINAL HANDOVER |
| QA + Validation | Pilot QA | Daily auto-QC | Daily auto-QC | L4 Monthly Audit | Full state QA | Final sign-off |
| Documentation | Pilot report | Weekly reports | AI go-live report | Monthly report | Monthly report | FINAL REPORT |

## Appendix C: Pole Condition Reference Guide (Field Card)

| Score | Label | What to Look For | Action |
| --- | --- | --- | --- |
| 1 | New / Excellent | No damage; perfectly vertical; clean surface; no corrosion; new appearance | Standard schedule |
| 2 | Good | Minor surface weathering; slight discoloration; fully structural; no visible lean | 3-year inspection |
| 3 | Fair / Watch | Surface rust patches; hairline cracks (not through); lean visible but <3°; some paint peeling | 1-year inspection; watchlist |
| 4 | Poor / Priority | Heavy rust; significant cracks; lean 3–7°; base erosion visible; bolts loose or missing | Work order — 3 months |
| 5 | Critical / Urgent | Structural failure imminent; severe lean >7°; broken base; multiple deep cracks; public safety risk | IMMEDIATE — flag and report now |

## Appendix E: Technology Stack Reference

| Layer | Component | Technology / Tool |
| --- | --- | --- |
| Mobile App | Survey App | React Native (Android-first, iOS future) |
| Mobile App | Offline Storage | SQLite with WAL mode |
| Mobile App | GPS | Native Android Location API + GLONASS/BeiDou |
| Mobile App | Camera | Native Android camera with EXIF metadata |
| Backend | API | Python FastAPI with async support |
| Backend | Database | PostgreSQL 15 + PostGIS 3 |
| Backend | Cache | Redis (map tiles + frequent queries) |
| Backend | Queue | RabbitMQ (300-device simultaneous sync management) |
| Cloud | Primary | AWS / Azure / NIC Cloud (TBD — May 4) |
| Cloud | Object Storage | S3 / Blob (photos — est. 200–300 TB total) |
| Cloud | Container | Docker + Kubernetes (EKS/AKS) |
| GIS | Map Server | GeoServer 2.x |
| GIS | Map Client | Leaflet.js + Mapbox GL JS |
| GIS | Desktop | ArcGIS 3.x (internal analysis) |
| AI | Framework | TensorFlow 2.x + PyTorch 2.x |
| AI | Type Model | EfficientNet-B3 (transfer learning) |
| AI | Condition Model | EfficientNet + YOLOv8 (defect detection) |
| AI | Tracking | MLflow (experiments + model registry) |
| AI | Labeling | Label Studio (self-hosted) |
| AI | Inference API | FastAPI + ONNX Runtime (CPU/GPU) |
| Dashboard | Frontend | React.js + Tailwind CSS |
| Dashboard | Charts | Recharts + D3.js |
| Monitoring | System | Grafana + Prometheus |
| Auth | System | OAuth 2.0 + JWT (role-based) |
| DevOps | CI/CD | GitHub Actions / GitLab CI |
| DevOps | IaC | Terraform (cloud infra as code) |

— END OF DOCUMENT —

Created by: Sharandeep Singh(NIBE SPACE)

MSEDCL Electric Pole Geo-Mapping & AI-Powered Infrastructure Intelligence System

Project Execution Blueprint v2.0  |  T0: May 4, 2026  →  T6: November 3, 2026  |  CONFIDENTIAL